## ACTUAL ACCOMPLISHMENT
ANNEX D
ANNUAL GENDER AN DEVELOPMENT (GAD) PLAN AND BUDGET AND ACCOMPLISHMENT
FY 2019
Region | : MIMAROPA Region | [5 empty] | Total Budget: | 2500000
Province | : Palawan | [5 empty] | Total GAD Budget: | 491634241.75
City/Municipality | : City of Puerto Princesa
Gender Issue or GAD Mandate | GAD Objective | Relevant LGU Program or Project | GAD Activity | Performance Indicator and Target | Actual Results | Approved GAD Budget | Actual Cost or GAD Expenditure | Variance or Remarks | Approved GAD Budget (7) | Actual cost of Exependiture (8) | Variance or Remarks (9)
(1) | (2) | (3) | (4) | (5) | (6)
I. SOCIAL DEVELOPMENT SECTOR
A. HEALTH
CLIENT-FOCUSED / GAD MANDATE
SOCIAL SERVICES SECTOR
Magna Carta of Women; The Indegenous Peoples Right Act of 1997 (IPRA) RA 8371 and Universal Health Care (UHC) ( AO 2010-0036) AND Primary Health Care | To ensure the immediate access of indigenous people to basic services including health and finacial risk protection | Indigenous Peoples Essential Social Services and protection program | Inclusion and Prioritization of IP Household in the PHIC Enrollment | 1000 IP household (600 female, 400 male) enrolled in PHIC city wide before the end of 2019 | Not Aprroved as IP strategies. | 350000 | 0 | No approved Budget
|  |  | Development and Distribution/Posting of Culture Sensitive IEC Materials for Health | Developed 200 IEC materials reproduced, posted and disseminated to 12 barangays with presence of IP community before the end of 2019 | Not Aprroved as IP strategies.
|  |  | Consultative Workshop | 4 Series of workshop with 100 participants (70% female participants and 30% male) before the end of 2019. | Not Aprroved as IP strategies.
|  |  | Development and Inclusion of IP Focused Referral System to Palawan Interhealth Facility Referral System; | IP focused referral system developed and included to Interhealth facility referral system before the end of 2019 | Not Aprroved as IP strategies.
|  |  | Roll Out Orientation to all Health Service Provider on Culture Sensitivity and Gender and Equality | 100% of 1200 (Medical Doctors,Midwives, Nurses,BHW, BNS, BSPO, BHIV Team) health service providers oriented on IP culutre sensitivity and GAD before the end of 2019 | Not Aprroved as IP strategies.
|  | Health Emergency Management Program | Basic Life Support Training for IP's | 500 qualified IP representative with 250 female and 250 male trained on Basic Life Support before the end of 2019 | Not Aprroved as IP strategies.
Magna Carta of Women (RA 9710) and The Responsible Parenthood and Reproductive Health Act of 2012 (RA 10354) | To ensure the right of children to assistance, including proper care and nutrition and special protection from all forms of neglect, abuse, cruelty exploitation and other conditons prejdicial to their development and reduce the incidence of infant and child mortality. | Expanded Program on Immunization; Maternal and Child Health Care and Nutrition Program | Immunization of all under 5 children against vaccine preventable diseases. | 100% of of eligible under 5 provided with vaccine/immunization from January to December 2019 | A total of 51735 ( 26,465 Male and 25,270 Female | 28000000 | 43851632 | 15,851,632.00 Additional Budget provided for other special programs.
|  |  | Immunization of Children & Adolescent Against Tetanus, Measles & Rubella. | 100% of 7,000 (4,200 females and 2,800 males) qualified children and adolescent for immunization provided with available vaccines from January to December 2019 | A total of 4,917 ( 3,346 Male and 1,571 Female )
|  | Malnutrition Prevention and Rehabilitation Program; | Deworming among under 5 Children. | 100% of eligible children provided with deworming medicines by the end of 2019 | A total of 31,325 ( 15,926 Male and 15,399 Female)
|  |  | Monthly weighing of under 2 children & Bi-Annual Weighing for 2-5 years old Children. | 100% of under 2 year old children weighed monthly in 2019; 100% of 0-71 months old children weighed bi annually in 2019 | A total of 26,657 (13,686 Male and 12,971 Female)
|  |  | Implementation, monitoring and evaluation of nutrition activities such as Operation Timbang, feeding program, micronutrient supplementation etc. | 100% of nutrition activities such as Operation Timbang, feeding program, micronutrient supplementation etc. implemented, monitored and evaluated from January to December 2019 | OPT, Sumpplementary feeding and micronutrient Simpplementation
|  |  | Provision of Micronutrient Supplementation to all qualified children under five years old | 100% of all qualified children under five years old provided with Micronutrient Supplementation from January to December 2019 | A total of 24408 (12 548 Male and 11860 Female)
|  |  | WASH in Child Development Centers | 100% of 159 Daycare Centers with functional Water, Sanitation and Hygiene facilities by the end of 2019 | A total of 159 daycare centers facilities functional with water, sanitation and hygiene.
|  | TB prevention , Management and Treatment Program | Children with TB provided with appropriate management and treament | 100% Children with TB provided with appropriate management and treament from January to December 2019 | A total of 49 children provided with appropriate management and treatment.
| To promote the rights and welfare of every person particularly couples, adult individuals, women and adolescent on reproductive health | Population control and Management Program | Provision of services and commodities for family planning to women of reproductive age | 100% of 35,000 women of reproductive age provided with family planning services and commodities from January to December 2019 | A total of 37,280 women provided services. | 3000000 | 4631694 | 184,636.00 Additional Budget allocated for commodities.
|  |  | Conduct of pre-marriage counselling , | 900 qualified applicants for Pre marriage counseling from January to December 2019 | A total of 908 couples provided.
|  |  | Information and dissemination campaign to communities on family planning and reproductive health | 3. 66 Barangays provided with Information on FAmily planning and reproductive health from January to December 2019 | A total of 38,167 ( 887 Male and 37,280 Female) provided information.
|  |  | monitor and evaluate planned activities for Responsible parenthood and Reproductive Health ; | 4. 100% of planned activities for Responsible parenthood and Reproductive Health implemented, monitored and evaluated from January to December 2019 | 1 BSPO training conducted with a total of 121 women participants and monitoring program implementation.
| Prevention , treatment and management of reproductive tract infections (RTI's), HIV and AIDS and other sexually transmitted diseases | STI/HIV -AIDS Program; Social Hygiene Clinic; Local AIDS Council | Develop, production and reproduction of IEC materials and advertisement for STI HIV AIDS prevention | 1 IEC materials developed, 5000 IEC materials reproduced before end of December 2019 | No IEC material developed. | 7269760 | 2727490 | 4542270
|  |  |  | 1 advertisement for STI HIV AIDS prevention produced before end of December 2019 | No advertisement produced.
|  |  | Orientation on HIV in the Worplace advocacy lectures | 10,000 (5000 females; 5000 males) food handlers given HIV 101 lecture and oriented on HIV in the Worplace Policy before the end of 2019
|  |  | STI and HIV 101 lectures | 100 female freelance sex workers before the end of 2019
150 establishment-based female sex workers
|  |  |  | 500 TB patients | A total of 238 clients.
|  |  |  | 2,000 pregnant | A total of 1858 clients.
|  |  |  | 500 couples in Pre-marriage counseling | A total of 908 couples provided.
|  |  |  | 10,000 Key Population (MSM/TG/YKP/students) | A total of 4988 key population.
|  |  | Conduct of AIDS Candlelight Memorial Celebration | 1,000 participants joined in AIDS Candlelight Memorial Celebration in December 2019 | A total of 500 parricipants attended.
|  |  | Conduct of World AIDS Day Celebration | 1,000 participants joined in World AIDS Day Celebration in May 2019 | A total of 500 parricipants attended.
|  |  | Conduct of HIV Testing Week | 100% of activities during the HIV Testing Week conducted as scheduled from January to December of 2019 | Not included in the approved budget.
|  |  | Seminar/ training/ updates of program coordinators (Provision of TEV) | 100% Seminar/ training/ updates of program coordinators on STI/HIV AIDS attended as scheduled and provided with TEV from January to December of 2019 | A total of 96 trained.
|  |  | Refresher Course for HIV Proficient Medical Technologists | 100% of Med. Techs attended the Refresher Course for HIV Proficient Medical Technologists and provided with registration fee and TEV from January to December of 2019 | A total of 34 medtech ttended.
|  |  | STI Laboratory Diagnosis and Management Training for Medical Technologists | 100% of Med. Techs.attended theSTI Laboratory Diagnosis and Management Training for Medical Technologists and provided with registration fee and TEV from January to December of 2019 | A total of 4 Medtech attended.
|  |  | STI Case Management Training for Nurses and Physicians | 100% of 37 nurses (4 males and 33 females) and 8 doctors (4 males and 4 females) attended the STI Case Management Training and provided with registration fee and TEV from January to December of 2019 | A total 60 Nurses attended.
PROVISION OF HIV TESTING SERVICES
|  |  | a. Registered/freelance female sex workers | 100% of MSM/TGSM, female sex workers, pregnant, TB patients, STI clients admitted for HIV Testing Services from January to December of 2019 | A total of 4,988 clients tested.
|  |  | b. Walk-in clients, including pregnant women, TB patients, STI clients |  | A total of 4,988 clients tested.
|  |  | c. Male/Transgender having sex with male |  | A total of 891 clients.
|  |  | Mobile HTS for Key Affected Population (MSM/TGSM) |  | A total of 891 clients.
|  |  | Mobile HTS for pregnant women in different barangays in the city | 100% of target pregnant women in different barangays in the city received HTS services by the end of 2019 | A total of 1858 clients.
|  |  | Mobile HTS for inmates of Iwahig Prison and Penal Farm and Puerto Princesa City Jail | 100% of target inmates of Iwahig Prison and Penal Farm and Puerto Princesa City Jail received HTS services from January to December of 2019 | A total of 57 clients.
|  |  | Referral of Reactive/Confirmed Positive for HIV to the Treatment Hub | 100% Reactive and HIV Confirmed Positive clients referred to the Treatment Hub for treatment, care and support from January to December of 2019 | 78% of HIV reactive reffered for treatment
LABORATORY DIAGNOSIS AND TREATMENT OF STI
|  |  | Laboratory diagnosis using Gram staining and Wet mount for: | 100% Gram staining and wet mount conducted to 2,000 clients from January to December of 2019
|  |  | a. Registered/freelance female sex workers |  | A total of 751 clients.
|  |  | b. Pregnant women |  | A total of 1586 clients.
|  |  | c. TB patients, STI clients and other walk-in clients |  | A total of 241 clients.
|  |  | Treatment of STI | 100% Clients with STI treated from January to December of 2019 | A total of 2592 clients.
Functionality of Health Facility for the management and link to treament and care of STI HIV AIDS patients ensured
|  |  | Peer Education Training for members of BHIV Team | 100% of Peer Education Training for members of BHIV Team conducted from January to December of 2019 | A total of 40 (22 Male and 18 Female) trained.
|  |  | Community-based Screening Training of Trained Peer Educators of BHIV Team | 100% of Community-based Screening Training of Trained Peer Educators of BHIV Team conducted from January to December of 2019 | A total of 40 (22 Male and 18 Female) trained.
MONITORING AND EVALUATION OF HIV AIDS PREVENTION PROGRAM
|  |  | Operational Support for Local AIDS Council | 100% LAC proposed/planned activities conducted from January to December of 2019 | A total 111 activities conductd.
|  |  | Monitoring and Evaluation of BHIV Team | 100% of activities on Monitoring and Evaluation of Performance of BHIV Team and Awarding of Most Active Barangay conducted by the end of 2019 | to be conducted on the 1st quarter 2020 ( not all brgy. Are orientedon the BHAT yet)
|  |  | Year-end Evaluation of Performance of BHIV Team and Awarding of Most Active Barangay | 100% of the Year-end Evaluation of Performance of BHIV Team and Awarding of Most Active Barangay conducted by the end of 2019 | not yet done because the training conducted in November 2019 only.
|  |  | Updates and Assessment Forum for HIV Trained MAPEH Teachers | 100% of the acitivity on Updates and Assessment Forum for 30 HIV Trained MAPEH Teachers conducted by the end of 2019 | Budget not released.
| to ensure responsive reproductive health services to promote women's health and safe motherhood | Maternal, Neonatal Child Health and nutrition program (MNCHN) Program, City Satellite Clinic Services; Expanded Local Health Board; Operational Support to DOH Retained Hospital (Ospital ng Palawan) | Prenatal & postnatal care services available in all BHS & City Satellite Clinics | 100% of 3000 pregnant and post partum women provided with prenatal and post natal services in all BHS and City Satellite Clinics by the end of 2019 | A total of 3,141 women provided services. | 8100000 | 4172404 | 3927596
|  |  | Training of midwives on BEMONC | 20 midwives trained on BEMONC by the end of December 2019 by the end of 2019 | Training Facility not available (fabella hospital)\
|  |  | Functional Maternal Death Review Team | 100% maternal deaths reviewed by the MDRT by the end of 2019 | CHO programs coordinator undergo formal training No MDR conducted.
|  |  | Enrolment of poor pregnant mothers to Philhealth | 100% of 20 poor pregnant mothers enroled to Philhealth by the end of 2019 | 20 poor pregnant mothrs enrroled.
|  |  | Referral of high risk pregnant women to hospital | 100% of high risk pregnant referred to hospital of choice from January to December of 2019 | A total of 938 reffered based on teenage pregnant registry.
|  |  | Provision of operational support /health human resource augmentation to Ospital ng Palawan | Operational support /health human resource augmentation to Ospital ng Palawanall from January to December of 2019 | Not Approved. |  |  | No approved Budget
| To establish or upgrade health facilities with adequate and qualified health personnel , equipment and supplies | City Health Facilities Enhancement Program | Construction of /complemtion of City Health Medical complex and provision of complete medical equipment to satellite clinics and BHS | Completion of City health Medical complex Phased 2; complete medical equipment provided to satellite clinics and other health facilities by the end of 2019 | Only 10,000,000 Aproved as 1st phase. | 100000000 | 0 | Budget was approved but project was not executed due personnel constraint in the city engineering office.
|  |  |  | Procurement of 3 ambulance for satellite clinics | 2 ambulance procured. | 6000000 | 2500000 | 3,500,000.00 Only 2 Ambulance had approved budget.
| To ensure non discriminatory treatment againts teen age pregnant, students and adolescent and ensure their access to guidance, counselling and health services/facilities | Adolescent Youth Health Program, CSWD, MNCHN Program, Family Planning program | Establishment of Intervention for Teen Age Pregnancy (I-TAP) Hub / YOUTH CENTER | 1 functional friendly, non-discriminating Adolescent Youth Corner established before the end of December 2019 | Not Aproved. Child Protection Unit was given priority. | 3300000 | 0 | Not Aproved. Child Protection Unit was given priority.
| to encourage and promote healthy lifestyle activities among women and girls | Non-communicable disease Prevention Program | conduct of household health profiling ; management and treatment of non-communicable diseases | 100% of women identified and profiled with non-communicable diseases provided with available health services and medicines from January to December of 2019 | A total of 2,209 patients provided services. | 1700000 | 1495000 | 205,000.00 variance DOH outsource training
| Ensure provision of support services and gears to protect women from occupational and health hazards | Oplan Linis Program; Solid Waste Management, Community Volunteer Health Workers | Provision of protective gears and Philhealth Insurance to job order/ contract of service for women employed or community volunteers of city government who are exposed to health hazards | 100% of women employed by CGPP on Oplan Linis and Solid Waste Management and Community Voluteer Health Workers provided with protective gears and health insurances from January to December of 2019 | Only community volunteer, health worker and Brgy. Officials provided. | 10000000 | 568000 | 9432000
Violation of privacy and confidentiality and security of Women with psychological instability/mental illness | To protect women, from harmful exposure to public, sexual assault and abuse due to inability to protect themselves caused by psychological instability/mental illness | Drop In Center for Mentally Ill Program | Assessment of patients/clients mental condition | 100% in patients assessed/ evaluated from January to December 2019 | A total of 264 ( 172 Male and 92 Female) assessed. | 2360000 | 1105000 | 1455000
|  |  | Temporary safekeeping of violent, hard to manage mentally disturbed patients | 100%of violent, hard to manage mentally disturbed patient from January to December of 2019 | A total of 60 patients.
|  |  | Referral to specialist/psychiatrist/ National Center for Mental Health | 100%. of assisted and referred to doctor/ psychiatrist /NCMH from January to December of 2019 | A total of 960 patients assted and reffered.
|  |  | Provision of medicine and food during safekeeping | 100% of referred/vagrant/ mentally ill patients provided with prescribed medications and food from January to December 2019 | A total of 856 patients provided.
| To assess, treat and link women drug dependents/surenderees and spouses of drug dependent men to care services and provided livelihood and her family | Community Rehabilitation Network | Provision of treatment, link to care and livelihood of women drug dependents/ and spouses of drug dependent men surrenderees and her family | 100% of women drug dependents/ surrenderees provided with treatment and linked to care and spouses of drug dependent men provided with livelihood from January to December of 2019 | A total of 1,178 individual provided. | 6303000 | 1180000 | 5,123,000.00 DOH provided HIV testing Kits
Vulnerability of women and girls to sexual assault due to open defacation practices and unsafe toilet | To reduce Vulnerability of women and girls to sexual assault due to open defacation practices and unsafe toilet | Water, Sanitation and Hygiene Program (WASH) Bayanihan para sa malinis na palikuran | Provision of sanitary toilet bowl to qualified household with women and/or girls | 100% of 500 household with women and/or girls provided with sanitary toilet bowls by the end of 2019 | 500 household with women/girls CR. | 600000 | 2237500 | There was additional budget proposal during the budget hearing
|  |  | Implementation and monitoring of WASH activities in 66 Barangays | 100% of WASH activities implented and monitored from January to December of 2019 | Conducted household inspection,sanitation practices and IEC.
|  |  | Evaluation of Barangays with Zero Open Defecation Practices | 15 Barangays with Zero Open Defecation Practices evaluated from January to December of 2019 | a TOTAL OF 29 Barangay declard ZOD.
Endangering health and lives of women due to unavailability of safe blood units and/or blood alternatives | Reduce mortality among women due to unavailability of safe blood units and blood alternatives | Operation of Blood Center/ Package Support for Blood and Blood Alternatives | Provision of support to patients needing blood units for processing of blood and /or blood alternatives | 100% of women, men and children requiring blood transfusion or blood alternatives provided support from January to December of 2019 | Implemented by the CSWD. A total of 8901 individuals provided with lood units. | 7000000 | 4806000 | 2194000
Inability/limited capacity of widow /widower or young dependents to provide decent burial to deceased family member/spouse | To provide needed immediate assistance to widow/widower and young dependents decent burial to deceased family member | Burial Assistance Program | Provision of casket and embalming services to requesting indigent widow/widower/young dependents with deceased family member/spouses | 100% of indigent widow/widower/young dependents with deceased family member/spouses requesting casket and embalming services from January to December 2019 | 748 coffin was providede to 518 poor female clients and 230 poor male clients asked free burial assistance for their deceased family member. 695 deceased was avail free embalmed, requested of 481 poor female clients and 214 poor male clients that asked freeburial assistance. | 13500000 | 6311575 | 7188425
SUB - TOTAL FOR HEALTH | [5 empty] | 200832760 | 75018295
B. EDUCATION
CLIENT-FOCUSED / GAD ISSUES
Increasing number of school dropout among boys, as they leave school to work in the farms, markets, piers, or the streets. School participation of children is often bound with their work responsibilities to their family. | To provide equal access to primary and secondary education of students from low-income families and marginalized group | Scholarship and Educational Assistance Program | Provision of educational assistance. Conduct responsible parenthood seminar on responsible parenthood & EIC forum (Information, Education and Communication) on the importance of education. | 330 student beneficiaries (198 females and 132 males) and parents (300PPCGEAP/30 IP) by the end of 2019. | PPCGEAP/IP not included in 2019 budget for the reason of free tuition in college level | 50900000 | 46056235 | 3943765
| To improve school performance of males and females students as elementary and secondary beneficiaries |  |  | 30,000 Kinder to Grade VI, 5,500 Grade VII to Grade X, 1,000 Grade XI to Grade XII student beneficiaries in Primary & Secondary schools and Balik Eskwela (total of 36,000 students/pupils) | 29,063 kinder to grade VI ( 15,208 Male and 13, 855 Female ) 7,992 Grade VII to Grade XII ( 4,041 Male and 3951 Female ) Junior and Senior High student beneficiaries in primary & secondary schools a total of 37,055 students/pupils.
| To provide equal access to both male and female students and OSYs for SPES Program | Special Program for the Employment of Students (SPES) and OSYs. | Provide employment to qualified students/youth aging 15-30 years old. | 482 SPES grantees (274 females and 208 males) provided empoyment at the end of 2019. | 482 SPES grantees 274 Females and 208 Males beneficiaries of the program provided SPES. | 3000000 | 1500000 | 1500000
SUB - TOTAL FOR EDUCATION | [5 empty] | 53900000 | 47556235
C. SPECIAL BENEFIT LEAVE
ORGANIZATION-FOCUSED / GAD MANDATE
Magna Carta of Women of 2009 (MCW-IRR Sec. 20 B6.g) | To provide access on special leave benefit for 504 permanent women employees of the City Government due to surgery caused by gyneacological disorders and other causes. | Human Resources Management Services | Provision for other Personnel Benefit to qualified permanent women employees of the City Government. | No. of female employees who availed the Special Benefit Leave subject to existing laws, rules and regulations at the end of 2019. | A total of 4 Female employee availed the special benefit leave. | 10000000 | 285112 | 9714888
SUB - TOTAL FOR SPECIAL LEAVE BENEFIT | [5 empty] | 10000000 | 285112.82
D. SHELTER
CLIENT-FOCUSED / GAD MANDATE
Magna Carta of Women of 2009 (MCW-IRR Sec. 24) | To implement policies and programs to ensure housing for women belonging to the marginalized sectors. | Support to City's Urban Poor Shelter Project | To provide assistance to ensure housing for women belonging to the marginalized sectors. | No.of beneficiary especially women provided shelter/housing by the City Government. | in 2018 the city housimg office already assist and provide shelter/housing program. | 5000000 | 5000000
| To provide easier access to affordable yet decent housing, especially for female headed households living in poverty. | City Urban Poor Affairs Program | To conduct inventory, validation and verification of informal settlers. | Conducted inventory, validation and verification of 5,000 households identified as informal settlers. (female 2,000; male 2,000 male and female children 1,000) | A total of 4,785 Household validated 2,230 Male and 2555 Female. | 904375 | 771467 | 132908
|  |  | To assist City Anti-Squatting Office to the families affected by demolition | Assisted 3,000 families affected by demolition (female 1,000; male 1,000 male and female children 1,000) | No assisted families affected by demolition because those are only side walk vendors.
|  |  |  | Pre-screened 600 applicants for housing program (300 female and 300 male). | only 47 ( 25 Male and 22 Female ) folders/requirements of applicants because other apllicants/awardees are having dis-agreement with the association and they don’t want to comply the requirements neede by the association.
|  |  | To assist walk-in clients from 66 barangays of Puerto Princesa. | Assisted 600 walk-in clients (female 400 and male 200) from 66 barangays of Puerto Princesa. | only 219 ( 122 Male and 97 Female ) walk in clients because more on of the clients are from rural barangay area and some of them inter-act through texting and calling using mobile phones.
Magna Carta of Women of 2009 (MCW-IRR Sec. 24 A.5) | To ensure gender-sensitivity and gender-responsiveness during the relocation, resettlement, demolition and eviction | Socialized Housing Development Project | To formulate, review and implement policies and guidelines to ensure gender-sensitivity and gender-responsiveness during the relocation, resettlement, demolition and eviction | No. of female and males relocatees provided with gender-sensitivity and gender-responsiveness policies and guidelines during the relocation, resettlement, demolition and eviction | 9 policies review, formulate and implement to 1,230 families ( 535 Male and 695 Female) | 8933479 | 8933479
SUB - TOTAL FOR SHELTER | [5 empty] | 14837854 | 14704946
E. SOCIAL WELFARE - SENIOR CITIZENS
CLIENT-FOCUSED / GAD MANDATE
Magna Carta of Women of 2009 (MCW-IRR Sec. 36 A,B,F) | To provide continous support services with senior citizens. | OSCA | Referral of SC for PhilHealth coverage | 2,239 Senior Citizens who are not yet covered by PhilHealth referred to PhilHealth Office | A total 2,338 ( 1446 Male and 892 Female ) Senior Citizens covered by PhilHealth. | 600000 | 600000
| To implement programs and services addressing gender-based violence, abuse and/or of woman senior citizens. |  | Referral of cases to CSWD for counselling of abused, neglected and abandoned SC, and their families, and for other interventions | All abused, neglected and abandoned SC seeking assistance referred to CSWD for counselling | A total of 6 ( 2Male and 4 Female ) abused, neglected refered to CSWD for Counselling.
| To enable Senior Citizens to attend social activities |  | Provision of assistive devices like wheelchairs, walkers, canes, etc. | Disabled SC provided with 20 wheelchairs, 10 walkers, 10 canes, and 9 hearing aids | 12 wheel chair ( 3 Male and 9 Female ) 2 walker ( female ) 10 canes ( 8 Females and 2 Males ) provided.
| To promote the rights of the SC in the city |  | Celebrate Senior Citizen Month every October 1-7, and related activities | 1 Senior Citizen Month celebrated | A total of 3226 ( 692 Male and 2533 females ) participated.
SUB - TOTAL FOR SOCIAL WELFARE-SENIOR CITIZENS | [5 empty] | 600000 | 600000
F. MARRIAGE AND FAMILY RELATIONS
CLIENT-FOCUSED / GAD MANDATE
Insufficient knowledge on effective parenting to 8,500 parents resulting to dysfunctional families (MCW-IRR Sec. 22 B.2- ) | To increase knowledge on effective parenting | Family Strengthening Program (Parents Effectiveness Services) (PES) | Conduct Effective Parenting Modular sessions | At the end of 2019, 3,000 poor families have access to social services and provided once a month modular session on parenting with positive result | 2631 (852 Male and 1779 Female ) poor families have access to social services. | 500000 | 554750 | There was additional budget proposal during the budget hearing
| To reduce reported incidence of neglect, women and children abuse through the conduct of intensive Pre-marriage counseling and separation among young couples |  | Conduct Pre-Marriage Counseling to young couples applying for marriage ages 18-24 years old with parent consent//advice and Facilitate marriage enhancement seminar | At the end of 2019, 300 of young couples attended Pre-Marriage Counseling and monitored after 1 year of marriage through Parent Congress or Marriage Enhancement Seminar. | A total of 988 ( 494 Male and 494 Female ) attende Pre-Mariage counseling.
| To empower women and their families city wide by increasing awareness on family members responsibilities |  | Facilitate Family Week Celebration every last week of September with approved City Ordinance No. 760 - Institutionalizing the celebration of family weeks every month of September | 2,000 Families with 90% women participated Family week Celebration on the last week of September 2019. | A total of 2857 ( 803 Male and 2054 Female ) participated on the family week celebration.
| To improve access of VAWC victims for immediate intervention/action from concern agencies |  | Strengthen coordination with VAWC desk/coordinator in 66 barangays | 100% reported VAWC cases assisted/provided with services needed. VAWC victims assisted of their immediate need if not filed complaint against the perpetrator. Monthly monitoring and follow-up will be done by the social worker | 100% reported victims were assisted/provided with services.
|  |  |  | 50% functional VAWC Desk with logbook/records of reported VAWC cases in their brgy. Intervention immediately provided to the victim | 50% functional VAWC Desk with log book/records of reported cases in the barangay
SUB - TOTAL FOR MARRIAGE AND FAMILY RELATIONS | [5 empty] | 500000 | 554750
G.SOCIAL WELFARE-GIRL CHILDREN
CLIENT-FOCUSED / GAD MANDATE
Low access of neglected, exploited, vulnerable and abused children in barangay to immediate needed social interventions. | To increase access of neglected, exploited, vulnerable and abused children in barangay to immediate needed social interventions by providing technical assistance to BCPC. | Strengthening Barangay Council for the Protection of Children Program | Conduct orientation/re-orientation to BCPC in 66 barangays | 66 barangays provided with BCPC training or technical assistance. At least 80-90% BCPC are functional by the end of 2019 | 66 BCPC provided with Technical ssistance Ideal - 5 Mature - 15 Progresive -25 Basic - 21 based on 2018 result of BCPC functionality assesrment | 1508000 | 692000 | 816000
|  |  | Conduct lecture on laws and policies of children to 66 brgys | 66 barangays/BCPC members attended lecture/discussion on laws and policies of children before end of December 2019 | A total of 1863 ( 501 Male and 1362 Female ) attended. 15 Barangay
|  |  | Conduct children fora to clustered barangays | Children fora conducted to 66 barangays before the end of 2019 | A total of 2642 ( 1142 Male and 1500 Female )
| Assist in organizing the children sector in the community |  | Facilitate implementation of BCPCs activities in 66 baragngays. | By the end of 2019, BCPCs activities successfully implemented to 66 brgys. | 57 Barangay facilitate implementation of BCPC activities.
SUB - TOTAL FOR SOCIAL WELFARE-GIRL CHILDREN | [5 empty] | 1508000 | 692000
H. GENDER-BIASED VIOLENCE/PROTECTION FROM ALL FORMS OF VIOLENCE
CLIENT-FOCUSED / GAD MANDATE
Magna Carta of Women of 2009 | To ensure availability of local facilities or offices providing support servies such as counseling, temporary shelter and child care for VAW victims. | Operation of GAD House | Provision of temporary shelter and services for women victims of violence | 100% of women victims of violence seeking help/temporary shelter assisted from January to December 2019 | A total of 442 cases. No case for temporary shelter. | 1958000 | 2070742 | There was additional budget proposal during the budget hearing
|  | GAD Women Program | Conduct of Womens Month Celebration activities | 100% of planned activites for Women's Month Celebration conducted in March 2019 | A total of 12 activities conducted. A total of 3758 women participants.
|  |  |  | 100% of women victims referred to concerned agency/offices for further management | A total of 442 cases.
|  | Drop in Center for Mentally Ill Program | Assessment of patients/clients mental condition | 100%of psychotic vagrants safekept and traced and reintegrated to family | A toal of 10 psychotic vagrants safekept traced and reintegrated to family. | 1777100 | 1045000 | 732100
|  |  | Temporary safekeeping of violent, hard to manage mentally disturbed patients | 100% of violent/ hard to managed patient transported to NCMH for further medication and treatment from January to December 2019 | A total of 4 patient transported to NCMH.
|  |  | Referral to specialist/psychiatrist/ National Center for Mental Health | 100% in patients assessed/ evaluated from January to December 2019 | A total of 960 patients assessed.
|  |  | Provision of medicine and food during safekeeping | 100%. of assisted and referred to doctor/ psychiatrist | A total of 960 patients assisted and refered.
|  |  |  | 100% of referred/vagrant/ mentally ill patients provided with prescribed medications and food from January to December | A total of 960 patients provided.
|  | Services for Minors | Conduct/facilitate case conference for parents/couple with marital problem to discuss issues regarding custody of their children | 329 parents invited , attended and participated for case conference with agreement reach for the welfare of children | A total of 1260 ( 630 Male and 630 Female ) attended. | 2801500 | 721500 | There was additional budget proposal during the budget hearing
|  |  | Conduct counseling to parents/couple who failed to abide with the agreement | 1,080 parents underwent counseling & other Social Welfare interventions. Continuous follow-up and monitoring to make sure they follow what has been agreed during counseling | A total of 2544 ( 1255 Male and 1289 Female )underwent counseling and other social welfare intervention.
|  |  | Provide fro temporary place house in group home/center for protection while social worker is working with their parents for preparation of their release after months in custody. | 78 children temporarily placed at the center. Child/children will be returned to their parent's custody at least after 3-6 months period except those children who are not yet prepared to go back to their family/parents. | A toal of 241 ( 124 Male and 117 Female ) temporarily placed at the center.
|  |  | Conduct counceling and daily lie skill sessions while at the center. | 101 children retruned to their parent's custody at least after 3-6 months period. | A total 297 ( 204 Male and 93 Female ) Children returned to their parents custody.
|  |  | House parents with the social worker conducted activities for them, food preparation and other social services needed for their welfare. | 764 CICL's underwent counseling. | A total 246 (235 Male ND 11 Female ) underwent counseling.
|  |  | Conduct follow up and monitoring of children upon return to their parents in coordination with partner agency in the barangay | 106 chidren (60 males,; 46 females) ptrovided with financila assistance for their food while at the center. This will be a ear round service for the children. | A total of 197 ( 86 Male and 111 Female ) provided financial assistance
SUB - TOTAL FOR GENDER-BIASED VIOLENCE/PROTECTION FROM ALL FORMS OF VIOLENCE | [5 empty] | 6536600 | 2792242
I. SOCIAL PROTECTION
CLIENT-FOCUSED / GAD MANDATE
Magna Carta of Women of 2009 (MCW-IRR Sec. 30 E) | To develop and implement community based social protection schemes and programs for women with disabilties. | PDAO | Provide livelihood/skills training for women PWDs | Number of livelihood and management training given to women PWDs for the FY 2019 | A total of 5 livelihood training conducted. | 11695736 | 11430228 | 265508
|  |  |  | Number of women PWDs given livelihood training and other resources from 2nd - 4th quarter 2019 | A total of 67 women participated.
|  |  |  | Number of trained women PWDs able to start an income generating activity 3 months after the training | A total of 67 women able to start an income generating.
|  |  | Conduct of different PWD activities and celebrations | Number of activities and attendees in activities and celebrations. | A total of 6 activities conducted. A total of 3,200 participated. 1336 Male and 1864 Female
Magna Carta of Women of 2009 (MCW-IRR Sec. 30 B.3) | To mainstream poverty reduction programs and services with social protection at the local level. | Practical Skill and Development Program | Faciltate the implementation of poverty reduction activities to target barangays/ community | poverty reduction activities implemented to target barangays/communities by the end of 2019 |  | 78750 | 78750
|  |  | Prepare project Proposal for skills training identified by the group of women | 5 Project/Training proposals prepared and submitted. Approved project Proposals | 5 Approved project Proposals. | 10000 | 10000
|  |  | Conduct/facilitate skills training to 5 cluster areas with 25 women/mothers participants | 125 women/mothers provided skills training with training materials, meals/snacks, and certificate of training | A total of 239 women provided skills training. | 200000 | 200000
|  |  | Conduct meeting/capacity building to equip them in managing their project or finances | 125 women undergo capacity building, and gain knowledge in project and financial management | A total of 239 women provided capacity building. | 20000 | 20000
|  |  | Profiling of women attended Practical skills training for future monitoring of what happen after | 125 of women monitored after the training. Women become economically productive. Established an income generating project | A total of 135 mwomen monitored.
|  |  | Facilitate/assist referral for employment/capi-tal assistance | 50 of women referred and open-employed/self-employed | A total of 12 women refered and open-employed/self employed.
|  | Medicare Para sa Masa | Conduct IEC (Information, Education and Counseling/ Campaign) and conduct survey/recruitment thru interview and assessment of indigent families | Number of IEC conducted by the end of 2019 | A total of 2083 ( 1025 Male and 1058 Female ) IEC conducted | 4643880 | 9,000.000.00 | There was additional budget proposal during the budget hearing
|  |  |  | 1,928 poor families oriented, recruited and applied Philhealth Insurance for Membership sponsored by the City Government. Have access to less hospital bills during confinement | A total of 2083 ( 1025 Male and 1058 Female ) oriented.
|  | Services for Families Affected by Demolition | Information & education campaign and counseling | 50 of Mothers/women/children is affected families provided with relief assistance during demolition. Families are accommodated and provided with temporary shelter and basic needs | A total of 58 mothers/women/children is affected families provided with relief assistance during demolition. | 100000 | 0 | No approved Budget
|  | Community Based Women and Child Disaster Evacuation Management Center | Development of Community based participatory 3 dimensional mapping. | Construction of 1 Evacuation Center 100% of evacuees women without secured /stable job provided with livelihood training while in the evacuation centers ( in the event /occurrence of disaster) | Construction of the evacueation center is on progress and it was executed by the city engineering office. | 54000000 | 52339005.65 | 1660994.35
|  |  | Establishment of gender sensitive evacuation centers with child friendly spaces and safe washing area |  | Procured 120 sets of foldable family and child friendly space, modular tent.
|  |  | Procurement of collapsible breasfeeding tents | 100% of Evacuation centers provided with collapsible breasfeeding tents | Procured 120 sets of foldable family and child friendly space, modular tent.
|  |  | Prompt resumption of educational services for children | 100% evacuees children availed the educational services while in the evacuation centers | children evacuees provided with educational services at the evacuetion center.
|  |  | Provision of food and non-food items to every household with special consideration to children with special needs | 100% of household provided with food and nonfood items, and supplements / Ready to Use Therapeutic Food (RUTF) | Distributed of 108 food and NFI to the family of fire incident in Brgy. San Miguel, Model, Bacungan, Tagbinet, Inagawan, Tiniguiban and atleast 5 infant and maternity kit.
|  |  | Provision of reqular health services in the evacuation center | 100% of evacuees provided with health services while at evacuation centers | A total of 108 family evacuees provided with health services.
|  |  | Provision of temporary and permanent toilet facilities/amenities |  | Available portable toilet for the evacuation area.
|  |  | Ensure availability of safe water |  | Purchased of 20 pieces bulk water container for evacuees.
|  |  | Procurement of additional ambulance to ensure quick medical response. |  | Funde to te next fiscal year containuing fund (capital outlay) and additional to 3 unit ambulance procure in 2020
|  |  | Conduct of Basic Life Support Training to Barangay and/or community, and organize Barangay Health Emergency Response Team |  | 3 days Basic Life support training conducted with a total of 33 ( 16 Male and 17 Female) paticipants.
|  |  | Provision of financial support for relocation during rehabilitation phase |  | A total of 58 women provided.
|  |  | Conduct of livelihood training and provision of start up fund for women in the evacuation center |  | A total of 715 Femaleclients assisted/facilitated through financial assitance for livelihood.
|  |  | Provision of psychosocial inervention to disaster victims |  | A total of 1045 (330 Male and 715 Female)clients assisted.
|  | Aid to Individual in Crisis Situation | Facilitate the implementation of AIC situation program activities city wide | AIC Situation program implementation facilitated through provision of livelihood projects to 750 clients by the end of 2019 | A total of 1045 (330 Male and 715 Female)clients assisted/facilitated through financial assitance for livelihood. | 1712100 | 1712100
|  |  | Information Education Campaign Counseling | 3,000 of Clients / Women /mother are able to identify resources to cope up their needs in time of crisis situation | A total of 3086 ( 965 Male and 2121 Female ) identify resources to cope up their needs in time of crisis situation.
|  | Facilitate the implementation ofDisaster Relief assistance activities city wide | Disaster Relief Assistance Program+180:208180180:208 | Regular worker: Ms. Gilda U. Tadjurie,RSW- SWO III Hired 1 Job Order | Hired 1 Job Order
|  |  | Conduct re-orientation/training of brgy. Officials/volunteers regarding Disaster management | 100% of brgy officials in 66 brgys. Attended training/ re-orientation on Disaster management and able to give immediate response during disaster | A total 5 training conducted. A total of 414 ( 141 Male and 220 Female ) attended.
|  |  | Conduct intake interview to affected families and provision of relief goods. | 3,000 of Evacuees/ victims of disaster provided with relief assistance. And able to Cope w/ their needs | a total of 58 evacuees/victims provided with relief assistance.
|  |  | Prepare documents for attachment to avail Financial assistance | 3,000 of affected families provided with Financial assistance | A total of 1015 ( 300 Male and 715 Female ) provided with financial assitance.
Low access of marginalized sector specially women children and their families in Geographically Isolated and Disadvantage Barangays to various social sersvices | To bring the social services closer/accessible to marginalized sector especailly women, children and their families in Rural/Geographically Isolated and Disadvantage Barangays of Puerto Princesa | Ugnayan sa Barangay | Provision of various social services to Rural/GIDA Barangays: (Veterinary, Agriculture, Health, Nutrition, Sanitation, Social Welfare, Civil Registration, Enginering; PDAO;Senior Citizen Services) | Conduct Ugnayan in 31 Rural/Geographically Isolated and Disadvantage Barangays barangays of Puerto Princesa City with 37,500 beneficiaries (22,000 females and 15,500 males). | A total of 39,806 ( 26,761 Male and 23,045 Female )beneficiaries. | 10000000 | 30936683 | There was additional budget proposal during the budget hearing
Low participation of OSY especially females to various community activities and programs. | To increase level of participation of OSY especially females to various community activities and programs. | Unlad Kabataan | Organize/re-organize Pag-asa Youth Association of the Philippines (PYAP) city wide | 8 PYAP organizations organized by the end of 2019. | A 58 PYAP organized. | 4405000 | 1071000 | 3334000
|  |  | Provision of other social support services under Unlad Kabataan Program | Number of youth benefited from the program | A total of 1285 ( 725 Male and 560 Female ) benefitted from the program
SUB - TOTAL FOR SOCIAL PROTECTION | [5 empty] | 96865466 | 106797766
II. ECONOMIC DEVELOPMENT CLUSTER
A. AGRICULTURE and FOOD SELF-SUFFICIENCY
CLIENT-FOCUSED / GAD MANDATE
Low participation of male in Skills Training | To increase the number of male participants in skills training/seminar for livelihood | Institutional development and livelihood supprt to farmers and fisherfolks | Conduct of Appropriate Tecnology Trainings and ensure farmers and fisherfolks adoption through application of technology in their areas. Privision of Agricultural and fishery inputs to farmers | 40 Trainings conducted by the end of 3rd quater of 2019 to 1000 participants (750 males and 250 female). | A total of 42 training conducted. A total of 1,394 ( 695 Male and 735 Female ) participants. | 600000 | 600000
|  |  | Conduct of livelihood training and provision of seed materials focused on mariculture such as seaweds production and nursery, dispersal of motorized boat and materials for bottom set gill net fishing. | 26 Trainings conducted by the end of December 2019 to 400 participants (300 males and 10 females). | A total of 38 training conducted. A total of 1,352 ( 1,247 Male and 105 Female ) participants. | 2046675 | 2046675
21.4% of women population of the city with income below poverty line | To increase the income of women population below poverty line. | Organic Hog Raising Livelihood Project | Conduct training on Hog Raising | 300 females participated in the training (100% accomplished by the end of 4th quarter) | A total of 502 (199 Male and 303 Female ) individuals attended our livestock animal production seminar. | 600000 | 840000 | There was additional budget proposal during the budget hearing
|  |  | Provisions/Dispersal of healthy animal stocks | To disperse 102 heads of Organic Hogs to targeted clients in 15 barangays by the end of the 4th quarter. | A total of 137 organic hogs was dispersed to targetd clients in 15 barangays by the end of the 4th quarter.
|  | Duck Raising and Dispersal Livelihod Project | Provisions/Dispersal of healthy animal stocks | To disperse 3,000 heads of ducks to 136 families by the end of the year | A total of 2000 head ducks was dispersed to104 families by the end of the year.
|  |  | Conducted training/seminars on Duck Raising and Production | To conduct training/seminars to women, senior citizens, OSY & young farmers on duck raising & production in 24 barangays by the end of 2019 | A total of 502 (199 Male and 303 Female ) individuals attended.
|  | Poverty Alleviation thru Sustainable Livelihood Strategy Program | Provision of livelihood assistance to marginalized members of the community especially the females. | 300 women and their families provided assistance for their livelihood by the end of 2019 | A total of 746 women provided assistance. | 5000000 | 5000000
|  | NEGOSYO Center Livelihood Program | Provision of Skills Training
|  |  | a. Skills on Smoke Fish Processing | 50 fisher folks, fishermen, fishermen's wives, housewives (M:30 , F:20) | No Barangay Request | 124000 | 49750 | 74250
|  |  | b. Skills Training on Lamayo Processing | 40 fishermen wives, housewives | 1 trainng conducted, a total of 33 participants, 10 male, 19 female and 4 senior citizen.
|  |  | c. Skills Training on Meat processing | 30 women of PWD & Solo Parent | 3 trainings conducted, a total of 54 participants 2 male, 41 female, 8 PWD
|  |  | d. Skills Training on Rootcrop Chips | Women of Urban Barangays | No Barangay Request
Entrepreneurial Training
|  |  | a. Entrepreneurial enhancement and Market Mind Setting Training / Seminar | 30 women's food processor | 1 training conducted. A total of 21 participants, 4 Male, 17 female
|  |  | b. Entrepreneurial Enhancement Training cum Bonsai culture | (PWD & INDIGENT WOMEN) 30 of Urban Barangays attended the training entitled "Enhancement Training Cum Bonsai Culture on prepare the end of FY 2019 | 1 training conducted. A total of 62 participants, 11 Male, 30 female, 12 Senior citizen and 9 PWD
|  |  | c. Entrepreneurial Training on Business Expenses Saving Training (BEST) Game Workshop | 40 women's academe entrepreneurial students. | 2 trainings conducted, a total of 70 participants, 12 male, 53 female, 4 Senior Citizen and 1 PWD
Low access of women to safe and affordable public transport services and social infrastructures/utilities (Magna Carta of Women of 2009 (MCW-IRR Section 23 B 9.g) | To improve access of women and children to safe and affordable public transport services and social infrastructures/utilities. | PRDP Farm to Market Road | Construction and concreting of Bualbualan Farm to Market Road in Barangay Simpokan, Puerto Princesa City. | Accessible concreted Farm to Market Road in Barangay Simpokan at the end of 2019. | PRDP Farm to Market Road is constructive and concreted. | 31000000 | 31000000 | Date of completion April 30 2019. Inaugurated last July 19, 2019. A total of 100 ( 35 Male and 65 Female ) participants.
SUB - TOTAL FOR AGRICULTURE AND FOOD SELF-SUFFICIENCY | [5 empty] | 39370675 | 39536425
B. LABOR AND EMPLOYMENT
CLIENT-FOCUSED / GAD MANDATE
RA 8425 An Act Institutionalizing the Social Reform and Poverty Alleviation Program and Magna Carta of Women (MCW-IRR Sec. 25 D) | To provide skills training, counselling and other support services integrated with entrepneurship and GAD. | Community-Based Sustaintable Tourism (CBST) GEAR Up Program | Conduct of entrepreneural training, counseling and other support services to CBST organizations. | Conducted CBST GEAR-UP Capacity Building and Livelihood Program in twenty-four (24) CBST sites in Puerto Princesa. | 25 CBST Capacity Building and livelihood program. A total of 258 ( 100 Male and 125 Female ) participants. | 5690000 | 3320000 | 2370000
|  | Cultural Tourism Program for Indigenous People | Develop and conduct various tourism activities at the Batak Visitor Center | 10 various tourism activities developed and conducted at the Batak Visitor Center | 10 various activities conducted and developed. | 1500000 | 1500000
|  | Public Employment Services | To provide skills training to female and male members of the organization.groups or individual. | No. of Skills Training provided/conducted. No. of individuals who availed trainings. | A total of 7 trainings conducted. A total of 233 ( 58 Male and 175 Female ) trainees. | 400000 | 400000
| To provide opportunities that will help solo parents identify and resolve feelings of loneliness, grief, frustrations and others which affect their role performance | Services for Solo Parent Program | Conduct interview and counseling to solo parents (Walk-in, reach out or referral) needing assistance | 50 solo parents provided counseling. And continuous session as per schedule until he/she can cope up with his/her present situation | A total of 146 ( 37 Male and 109 Female ) solo parent provided counseling. | 230000 | 230000
| To provide learning opportunities that would enhance and improve the understanding, attitude and skills of solo parent in their responsibility in raising and managing their children while performing their dual/multiple roles at home. |  | Conduct skills training or refer to TESDA for short term vocational course | 50 Solo Parents provided with skills training/livelihood assistance or refers to TESDA for vocational course | A total of 140 ( 5 Male and 135 Female ) provided.
| To gain access to available resources and other support services that may be necessary for the solo parents and their children |  | Provide Financial or livelihood assistance for them to provide the needs of children left under their care | 40 Solo parents provided with financial assistance as starting capital of their livelihood to support the needs of their children. Solo parents augment income. To be monitored in a monthly basis | A total of 42 women solo parents provided.
| To organize and mobilize community based support system/growth groups of solo parents that will help strengthen their coping mechanisms towards solo parenting |  | Issuance of Solo Parent ID to government/private solo parent employee to avail 7 days privilege leave and for his/her child/children avail scholarship | 500 solo parents applied and provided Solo parent ID. Child/children studying in college availed discount or scholarship to school implementing guidelines as mandated in R.A. 8972. Solo Parents able to supervised/managed/accompanied his/her child/children’s activities as per guidelines in availing 7 days privilege leave. | A total of 1,070 ( 75 Male and 995 Female ) solo parent provide with solo parent ID.
|  |  | Conduct survey of solo parents and organize them into groups/association | 40 Solo Parents surveyed and Solo Parent groups organized. Solo Parent group members able to cope with their difficult situation as solo parents and actively participated activities in the community even render volunteer works. | A total of 94 ( 5 Male and 89 Female ) solo parents surveyed.
|  |  | Conduct Solo Parent Day every December | 80% of identified solo parents attended Solo Parent day. For them to be acquainted with other Solo parent from different barangays | A total of 262 ( 41 Male and 221 Female ) solo parent attended.
| To empower women/mothers thru provision of trainings on livelihood to augment family income | Self Employment Assistance Program (SEAP) | Conduct Social preparation and capability building to identified women/mothers needing additional capital assistance to augment family income | 40 Women extended capital assistance. 50% of women augment family income by the end of 2019 | A total of 135 women extended capital assistance. | 200000 | 200000
|  |  | Preparation/encoding and printing of individual project proposals, and processing with complete documents | 40 individual project proposals prepared and processed | A total of 147 proposal prepared and processed. | 10000 | 10000
|  |  | Conduct weekly visit/monitoring to women/mothers provided with trainings on livelihood. | 40 women/mothers visited/monitored. Women/mothers able to pay their monthly payment obligations regarding the loan amount for capital assistance which is payable for 2 years without interest. | A total of 135 women/mothers monitored and able to pay obligations for 2 years without interest. | 60000 | 60000
|  |  | Conduct meeting/ capability building to old and new women/mother beneficiaries for saving generations and mobilization fund | 20 women/mothers generated savings 20 women/mothers’ SKA associations with 400 members generated savings/capital build-up fund for sustainable livelihood projects | A total of 40 women/mother generated savings. A tota of 30 SKA women groups with 746 members. | 393750 | 393750
SUB - TOTAL FOR LABOR AND EMPLOYMENT | [5 empty] | 8483750 | 2797070
II. ECONOMIC DEVELOPMENT CLUSTER
A. AGRICULTURE and FOOD SELF-SUFFICIENCY
CLIENT-FOCUSED / GAD ISSUES
Increasing number of female and male job seekers | Employment creation, with emphasis on greater opportunities for women and men to secure decent employment and income. | Job Fair | Employers are invited to conduct job interview in a common date and place where jobseekers can apply. | No. of Job fair conducted/monitored and no. of applicants | A total of 11 Job Fair conducted. A total of 2853 ( 987 Male and 1866 Female ) applicants. | 220000 | 220000
|  | Local Recruitment Activity | Conduct of recruitment for Local employment at the City PESO Office. | No. LRA conducted and no. of applicants | A total 34 conducted A total of 1307 ( 457 Male and 850 female ) appllicants.
|  | Special Recruitment Activity | Conduct of recruitment for Overseas employment | No. of SRA conducted and no. of applicants | A total of 22 SRA conducted. A total of 266 ( 123 Male and 143 Female ) applicant.
|  | Registration of Job Applicants | Registration of applicant to PESO Employment Information System (PEIS) | No. of applicants registered | A total of 3798 ( 1531 Male and 2267 Female ) applicants registered.
|  | Job Referral | Qualified applicants referred. | No. of applicants referred | A total of 12738 ( 5487 Male and 7251 female ) applicants referred.
| To provide career coaching for High School students, employment coaching for all applicants and Labor Education to Graduating Students (LEGS) for better employability | Career Coaching | Conduct of Career Coaching | No of schools and students | A total of 13 Schools. A total of 1738 ( 757 Male and 981 Female ) students.
|  | Employment Coaching and Counselling | Conduct Employment Coaching and Counselling | No. of applicants | A total 2909 ( 1132 Male and 1777 Female ) applicants.
|  | LEGS | Conduct of LEGS | No. of students | 1 school. A 139 ( 63 Male and 76 Female ) students.
Increase the percentage of barangays with Day Care Centers from 86.36% to 100% | To increase attendance of 3-4 y/o children in Day Care Centers | Early Childhood Care and Development (ECDC) | Conduct orientation to barangay officials to disseminate the significance/importance of Early Childhood Care and Development | Number of barangay officials oriented from January to December 2019 |  | 13150000 | 15818842 | There was additional budget proposal during the budget hearing
|  |  | Conduct orientation to Child Development Workers to disseminate the significance/ importance of Early Childhood Care and Development | Number of Child Development Workers oriented from January to December 2019 | A total of 155 ( 2 male and 153 Female ) oriented.
|  |  | Conduct Parent Effectiveness Training | 100% fathers or mothers will be able to know the significance/ importance of enrolling their 3-4 years old children in Early Childhood Care and Development | A total of 25 fathers and 685 mother were able to know the significance of enrolling their children.
| To increase awareness of parents (fathers and mothers) on the significance/ importance of Early Childhood Care and Development for their 3-4 years old children |  | Conduct regular meetings with parents | 10 regular monthly meetings conducted, from January to March, and June to December 2019 | 10 regular meeting conucted.
|  |  | Conduct of Family Week Celebration on the last week of September | 1 Family Week celebrated September 2019 | 1 family week conducted.
|  |  | Recognition of Good Performing Day Care Children | Recognition rites done in all Day Care Centers in the city | A total of 1698 boys and 1669 girls child devt were recognized.
| To increase participation/ involvement/ attendance of fathers to the Child Development activities |  | Conduct orientation to fathers on their important roles and responsibilities to their small children (ERPAT) | 100% or 4,861 fathers will be able to attend to different activities of the Early Childhood Care and Development | 679 fathers able to attend the different activities .
| To promote children's rights |  | Conduct of Universal Children’s Month Celebration | 1 Universal Children's Month celebrated by last week of October to November 2019 | Universal Childrens month conducted.
|  |  | Day Care Workers’ Week | 1 Day Care Workers' Week celebrated by second week of June 2019 | Day Care workers week conducted.
| To upgrade and enhance the services to be given to the children ages 3-5 years old of Puerto Princesa |  | Attain the Child Development Workers' highest level in accreditation (5 stars/ level 3). (60 Barangays) | 100% or 170 Child Development Workers attain the highest level in accreditation (5 stars/ level 3) in 60 barangays covered from January to December 2019 | No Child Devt Workers attained the 5 star level 3 accreditation.
|  |  | Conduct of intensive training to Child Development Workers | 100%, or 15 Area Supervisors and 170 CDWs undergone intensive training on early child care and development from April to May 2019 | 200 cluster Area Supervisors and staff undergone training on child devt service program.
|  |  | Upgrading of Day Care centers, and play area | 10 Sets of outdoor playground devices, and facilities for 10 Cluster with toys, blocks and books | 5 sets of playground facilities and devices with toys, blocks and books were given to 5 child devt center.
SUB - TOTAL FOR LABOR AND EMPLOYMENT | [5 empty] | 14370000 | 16038842
III. INFRASTRUCTURE SECTOR
A. SOCIAL SUPPORT
CLIENT-FOCUSED / GAD MANDATE
Magna Carta of Women of 2009. Right of Marginalized Sectors to Equal access to basic services and facilities | To ensure availability of a multi-purpose hall that can be accessed/used by 129,590 female population of Puerto Princesa City. (source: 2016 projected population - PSA) | Puerto Princesa City Coliseum Management Services | Ensure the availablity/accessability of Puerto Princesa City Coliseum for the activities of women of Puerto Princesa. | No. of activities conducted by the female population of Puerto Princesa in the City Coliseum (eg. Women's Month Celebration etc.) | A total of 12 activities conducted. A total of 3662 women participants. | 17231918 | 15357086 | 1874832
| To promote the rights of women as leaders through active participation and community awareness | Tribal Affairs | Conduct orientation on Gender Sensitivity and MCW mandates | At least 3 women leaders are active members of Tribal Council (100% accomplished by the end of 3rd quarter) | A total of 689 women actively participated and 3 tribal women members. | 1492125 | 1514175 | There was additional budget proposal during the budget hearing
SUB - TOTAL FOR SOCIAL SUPPORT | [5 empty] | 18724043 | 16871261
IV. INSTITUTIONAL SECTOR
A. DEVELOPMENT ORIENTATION
CLIENT-FOCUSED / GAD MANDATE
Lack of knowledge/experience of the newly elected barangay officials with 363 males and 297 females on the existing laws particularly those that are gender-related, drafting of resolutions and ordinances, roles and responsibilities and postive work values. | To enhance/strengthen the legislative skills of the newly elected barangay officials on the existing laws particularly those that are gender-related, drafting of resolutions and ordinances, roles and responsibilities and postive work values. | Legislative Skills Enhancement Training for Barangay | Conduct of legislative skills enhancement activities to newly elected barangay officials of the City by the end of 2019. | 660 Barangay Officials trained Female : 297 or 44% Male : 363 or 56% | Already conducted the activity last 2017. | 400000 | 0 | No approved Budget - Already Conducted the activity.
SUB - TOTAL FOR DEVELOPMENT ORIENTATION | [5 empty] | 400000 | 0
B. ENTERPRISE DEVELOPMENT
CLIENT-FOCUSED / GAD MANDATE
Low access of women business investors in securing business permits and licenses. | To improve access of women business investors in securing business permits and licenses. | Business Permits and Licensing Ofice | Provide special lane especially for pregnant women and women with children, women senior citizens, and PDAO women in securing business permits and licenses. | 100% of taxpayers with complete requirements issued business/Mayor's Permit (pregnant women, PWD, Senior Citizen) | A total of 3,084 ( 630 Male and 2454 Female ) Senior Citizen, PWD, Pregnant Women and Women with infant accommodate/provided services through special lane | 50000 | 50000
SUB - TOTAL FOR ENTERPRISE DEVELOPMENT | [5 empty] | 50000 | 50000
GAD MAINSTREAMING
A. PLANNING, PROGRAMMING, BUDGETING, MONITORING AND EVALUATION
CLIENT-FOCUSED / GAD MANDATE
R.A. 9710 Magnan Carta of Women of 2009 | To capacitate the GFPS with necessary tools to enable them to develop, implement, audit and monitor gender perspectives of PPAS | Strengthening GAD Focal Points System | Conduct trainings on harmonized GAD planning and Budgeting (HGDG), Gender Analysis, Gender Responsive Work and Financial Planning, M&E, PIME and other relevant trainings on GFPS strengthening | ●1 Training-Workshop on Harmonized GAD Planning and Budgetting conducted by 1st Qtr of 2019 ● Training-Workshop on Gender Anlaysis (HGDG & PIMME) ● 1 Training-Workshop on Work and Financial Planning conducted by 1st Qtr of 2019 ● 1 Training-Workshop on GAD Monitoring and Evaluation conducted by 1st Qtr of 2019 | Conducted the first GAD Summit entitled Gender Responsive and child Governance attended by 66 Brgy. Official and GAD TWG/Focal of different offices of the City Government A total of 150 participants 68 male and 82 female. | 1000000 | 799000
| To increase the level of awareness ad uderstanding of city employees on GAD concepts, issues, concerns and mandates. |  | Conduct of Gender Sensitivity seminar with integration of VAW laws and Anti Secual Harrassment Act for city officials and employees. | Number of Gender Sensitivity Seminar conducted for city officials and employees by 2nd Quarter of 2019. | 1 Gender Sensitivity Conducted, a total of 150 participants 68 male and 82 female.
| To ensure that city personnel are gender sensitive and responsive in dealing with internal and external clients. |  | Conduct of Seminars on CEDAW. Magna Carta of Women and national laws an policies related to women for frontline service providers and field workers. | Number of seminar on CEDAW, Magna Carta of Women and national laws and policies related to GAD by December 2019. | 6 Seminar/training conducted.
|  |  |  | 100% of frontline service providers attended seminar on CEDAW, magna Carta for Women nd relevant nationla laws anf policies. | A total of 2013 (569 Male and 1444 Female ) frontline service providers.
|  |  |  | Gender-sensitive and responsive frontline service providers. | A total of 150 (68 Male and 82 Female ) frontline service providers.
SUB - TOTAL FOR GAD MAINSTREAMING | [5 empty] | 1000000 | 799000
ATTRIBUTED PROGRAMS
Title of LGU Program or Project (8) |  |  | HGDG Design Funding Facility / Generic Checklists Score (9) | Total Annual Program / Project Budget (10) | GAD Attributed Program / Project Budget (11) | Lead or Responsible Ofice (12) | Actual Cost or GAD Expenditure | Variance or Remarks
Solid Waste Management Program |  |  | 9.34 | 24889687.5 | 12444843.75 | City Mayor's Office | 49941397
Oplan Linis Program |  |  | 10.34 | 22420500 | 11210250 | City Mayor's Office | 22520500
GRAND-TOTAL I, II, III, IV, V + GAD MAINSTREAMING | [6 empty] | 491634241.75
Prepared by: |  | Approved by:
CARLOS G. ABOGADO, JR. |  | LUCILO R. BAYRON
Chairperson, GFPS TWG |  | Local Chief Executive