## Sheet1
|  |  |  | CITY GOVERNMENT OF PUERTO PRINCESA | [9 empty] | Department of Budget and Management Procurement Monitoring Report as of month/day/2006
Supplemental Annual Procurement Plan for FY 2021
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? (Yes/No) | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Project) | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Delivery/ Accept
5-02-03-070 | Public Health Emergency Response for Corona Virus Disease - 2019 (Covid-19) Pandemic Program (Vaccination Project) Drugs and Medicines | CHO | NO | NP-53.2 Emergency Cases | - | - | 2021-02-01 | 2021-02-01 | GoP | 272938000 | 272938000
20% Dev't Fund 5-02-03-070 | Public Health Emergency Response for Corona Virus Disease - 2019 (Covid-19) Pandemic Program (Vaccination Project) Drugs and Medicines | CHO | NO | NP-53.2 Emergency Cases | - | - | 2021-02-01 | 2021-02-01 | GoP | 50062000 | 50062000
| Conduct of feasibility study and Detailed Engineering Design for PPC Fishports (Main and Satellite) | CED | NO | Competitive Bidding | 2021-08-03 | 2021-08-31 | 2021-09-01 | 2021-09-03 | GoP | 33000000 | 0 | 33000000
| Construction of Philippine National Police Building in Barangay Napsan | CED | NO | Competitive Bidding | 2021-08-03 | 2021-08-31 | 2021-09-01 | 2021-09-03 | GoP | 22500000 | 0 | 22500000
5-02-99-990 | Public Health Emergency Response for Corona Virus Disease - 2019 (Covid-19) Pandemic Program (Vaccination Project) Drugs and Medicines | CHO | NO | NP-53.2 Emergency Cases | - | - | 2021-05-31 | 2021-05-31 | GoP | 303359000 | 303359000
5-02-13-030 | Installation of Reflectorized Thermoplastic Pavement Markings of Various City Roads | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 3000000 | 3000000 | 0
5-02-13-030 | For Asphalt Overlay of Entrance Road At Batching Plant | CED | NO | NP-53.9 - Small Value Procurement | 2021-10-18 | 2021-10-21 | 2021-10-25 | 2021-10-26 | GoP | 700000 | 700000 | 0
20% Dev't Fund 1-07-05-080 | Purchase of Equipment for Batching Plant: 1. 3 units 10 cu.m Mixer Truck | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 15600000 |  | 15600000
20% Dev't Fund 1-07-05-080 | 2. 1 unit 6 cu.m Mixer Truck | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 3700000 |  | 3700000
20% Dev't Fund 1-07-05-080 | 3. 2 units Tipper Dump Truck with Hydraulic Tailgate for concrete paver | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 10000000 |  | 10000000
20% Dev't Fund 1-07-05-080 | 4. 1 unit Asphalt Distributor Truck | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 3280000 |  | 3280000
20% Dev't Fund 1-07-05-080 | 5. 2 units Excavator Steel Truck | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 15800000 |  | 15800000
20% Dev't Fund 1-07-05-080 | 6. 1 unit Asphalt Tanker Truck with Asphalt Pump | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 4500000 |  | 4500000
20% Dev't Fund 1-07-05-080 | 7. 1 unit Cement Screw Conveyor with Hopper | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 2500000 |  | 2500000
20% Dev't Fund 1-07-030-050 | Installation of Rural Barangay Solar Streetlights | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 30000000 | 0 | 30000000
20% Dev't Fund 1-07-030-050-99 | Site Preparation and Enbankment of Public Market Site in Barangay Salvacion | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 1500000 | 0 | 1500000
20% Dev't Fund 1-07-030-050-99 | Horizontal Development of Maslog Relocation Site | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 18000000 | 0 | 18000000
20% Dev't Fund 1-07-04-010 | Finishing of Bahay Pag-asa CICL Boys | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 6000000 | 0 | 6000000
20% Dev't Fund 1-07-03-010-1 | Concreting of Catumbal Road at Purok Pagkakaisa | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 6009000 | 0 | 6009000
20% Dev't Fund 1-07-03-010-1 | Concreting of Access Road Between PSU and Sports Complex | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 4937200 | 0 | 4937200
20% Dev't Fund 1-07-03-010-1 | Concreting of Castro Road III (remaining portion) | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 934500 | 0 | 934500
20% Dev't Fund 1-07-03-010-1 | Concreting of Mahogany Road (remaining portion) | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 800000 | 0 | 800000
20% Dev't Fund 1-07-03-010-1 | Concreting of Access Road to Sports Complex | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 11174600 | 0 | 11174600
20% Dev't Fund 1-07-03-020-8 | Construction of Drainage at Muslim Cemetery, Bgy. San Jose | CED | NO | Competitive Bidding | 2021-10-18 | 2021-11-08 | 2021-11-11 | 2021-11-12 | GoP | 993200 | 0 | 993200
| Construction of Engineering and Architecture Builidng, Sta. Monica | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 24000000 | 0 | 24000000
| Construction of GSO Warehouse, Sta. Monica | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 16000000 | 0 | 16000000
| Concreting of Durangol FRM, Inagawan | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 9920000 | 0 | 9920000
| Opening and Gravelling of RAC FMR to Highway (CBFM Road), Salvacion | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 4312500 | 0 | 4312500
| Concreting of Sta. Cruz Road III to Daungan FMR, Sta. Cruz | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 9393000 | 0 | 9393000
| Concreting of Bukang-Liwayway HOA Road at Purok Masipag, Bancao-Bancao | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 5250000 | 0 | 5250000
| Concreting of Road from Pier to Entrance to Baywalk, Bagong Pag-asa | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 2665000 | 0 | 2665000
| Concreting of Gabuco Road, Bagong Sikat | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 4100000 | 0 | 4100000
| Concreting of Ipil Street (Riverside Road), Irawan | CED | NO | Competitive Bidding | 2021-09-10 | 2021-09-30 | 2021-10-04 | 2021-10-05 | GoP | 10250000 | 0 | 10250000
| Completion of Maligaya Road (Tanguegue Road), Mandaragat | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 2187500 | 0 | 2187500
| Concreting of Pensylvannia Road at Purok Bakawan, Mandaragat | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 1837500 | 0 | 1837500
| Concreting of Villa Isidra Road Network, Milagrosa | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 8815000 | 0 | 8815000
| Concreting of Pio Manlavi Road, Milagrosa | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 8347500 | 0 | 8347500
| Concreting of San Jose New Market By-Pass Road (South to North National Highway), San Jose | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 40211000 | 0 | 40211000
| Concreting of Suha Road with Drainage System, San Jose | CED | NO | Competitive Bidding | 2021-08-20 | 2021-09-20 | 2021-09-12 | 2021-09-13 | GoP | 17842500 | 0 | 17842500
| Concreting of Road Going to Kuyba Almoneca, Sitio Masikap, San Jose | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 4100000 | 0 | 4100000
| Concreting of Road Leading to Emerald Aplaya Beach/Microtel, San Manuel | CED | NO | Competitive Bidding | 2021-08-20 | 2021-09-20 | 2021-09-12 | 2021-09-13 | GoP | 15050000 | 0 | 15050000
| Concreting of Cabiguen Road (Armando Lopez), San Miguel | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 9012500 | 0 | 9012500
| Concreting of Road Going to Puerto Princesa Science High School with Sidewalk and Drainage System, Sta. Monica | CED | NO | Competitive Bidding | 2021-08-20 | 2021-09-09 | 2021-09-12 | 2021-09-13 | GoP | 17511000 | 0 | 17511000
| Concreting of Dimalanta Road to Ranchero Road, Sta. Lourdes | CED | NO | Competitive Bidding | 2021-09-10 | 2021-09-30 | 2021-10-04 | 2021-10-05 | GoP | 14000000 | 0 | 14000000
| Concreting of Subdivision Road at Pagkakaisa Relocation Site, Sicsican | CED | NO | Competitive Bidding | 2021-09-10 | 2021-09-30 | 2021-10-04 | 2021-10-05 | GoP | 10250000 | 0 | 10250000
| Concreting of Mabuhay Relocation Road Network Block 3, Sicsican | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 7236500 | 0 | 7236500
| Concreting of Road Leading to City Slaughterhouse with Sidewalk and Drainage System, Tagburos | CED | NO | Competitive Bidding | 2021-08-20 | 2021-09-20 | 2021-09-12 | 2021-09-13 | GoP | 20905500 | 0 | 20905500
| Concreting of Pablico Road 2, Tiniguiban | CED | NO | Competitive Bidding | 2021-09-10 | 2021-09-30 | 2021-10-04 | 2021-10-05 | GoP | 6877500 | 0 | 6877500
| Concreting of Binduyan Cemetery Circulation Road, Binduyan | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 4100000 | 0 | 4100000
| Concreting and Widening of Inagawan Road with Sidewalk and Drainage System Phase II, Inagawan | CED | NO | Competitive Bidding | 2021-09-10 | 2021-09-30 | 2021-10-04 | 2021-10-05 | GoP | 18500000 | 0 | 18500000
| Concreting of Road Leading to Iwahig Heritage Center, Iwahig | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 16681500 | 0 | 16681500
| Concreting and Widening of Kamuning Road with Sidewalk and Drainage System Phase II, Kamuning | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 45140000 | 0 | 45140000
| Concreting of Road from Purok Kaunlaran to Mini City Hall, Luzviminda | CED | NO | Competitive Bidding | 2021-08-20 | 2021-09-20 | 2021-09-12 | 2021-09-13 | GoP | 11719000 | 0 | 11719000
| Concreting of Paglaum to Cemetery Road, Mangingisda | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 5850000 | 0 | 5850000
| Concreting of New Panggangan Road Network, New Panggangan | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 4800000 | 0 | 4800000
| Concreting of Road Leading to Ugong Rock, Tagabinet | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 5850000 | 0 | 5850000
| Construction of Dormitory at Luzviminda Rural Service Center, Luzviminda | CED | NO | Competitive Bidding | 2021-09-10 | 2021-09-30 | 2021-10-04 | 2021-10-05 | GoP | 10000000 | 0 | 10000000
| Completion of Mini City Hall (Fence, Gate, Parking, Landscape and Outdoor Lighting), Luvziminda | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 2500000 | 0 | 2500000
| Completion of Mini City Hall (Fence, Gate, Parking, Landscape and Outdoor Lighting), Macarascas | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 5000000 | 0 | 5000000
| Completion of Mini City Hall (Fence, Gate, Parking, Landscape and Outdoor Lighting), Napsan | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 5000000 | 0 | 5000000
| Construction of Dormitory at San Rafael Rural Service Center, San Rafael | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 10000000 | 0 | 10000000
| Completion of Mini City Hall (Fence, Gate, Parking, Landscape and Outdoor Lighting), San Rafael | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 2500000 | 0 | 2500000
| Concreting of Irawan Agricultural Center Road Network Phase II, Irawan | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 40000000 | 0 | 40000000
| Construction of Public Toilet, Irawan Integrated Agricultural Center, Irawan | CED | NO | Competitive Bidding | 2021-08-20 | 2021-09-20 | 2021-09-12 | 2021-09-13 | GoP | 5000000 | 0 | 5000000
| Construction of Perimeter Fence at Irawan Agricultural Trading Center, Irawan | CED | NO | Competitive Bidding | 2021-09-10 | 2021-09-30 | 2021-10-04 | 2021-10-05 | GoP | 10920000 | 0 | 10920000
| Construction of Material Recovery Facility at Irawan Integrated Agricultural Center, Irawan | CED | NO | Competitive Bidding | 2021-09-10 | 2021-09-30 | 2021-10-04 | 2021-10-05 | GoP | 2007110 | 0 | 2007110
| Construction of Power House for Irawan Integrated Agricultural Center, Irawan | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 3541325 | 0 | 3541325
| Construction of Washing and Packing Building, Irawan | CED | NO | Competitive Bidding | 2021-09-10 | 2021-09-30 | 2021-10-04 | 2021-10-05 | GoP | 4732000 | 0 | 4732000
| Installation of Underground Electrical Line and Power Supply, Irawan | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 32000000 | 0 | 32000000
| Renovation/Improvement of Buenavista Satellite Clinic, Buenavista | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 1000000 | 0 | 1000000
| Renovation/Improvement of Inagawan Satellite Clinic, Inagawan | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 1000000 | 0 | 1000000
| Renovation/Improvement of Salvacion Satellite Clinic, Salvacion | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 1000000 | 0 | 1000000
| Completion of Balayong Park Road Network (Sidewalk/Drainage System), Sta. Monica | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 20000000 | 0 | 20000000
| Completion of Sports Complex Basketball Court (Lighting, Ring, Bleachers), Sta. Monica | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 6000000 | 0 | 6000000
| Completion of Sports Complex Indoor Court (Lighting and Bleachers), Sta. Monica | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 10000000 | 0 | 10000000
| Completion of Sports Complex Volleyball Court (Lighting and Bleachers), Sta. Monica | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 5500000 | 0 | 5500000
| Installation of Pump/Aerator for Waterpod at Balayong Park, Sta. Monica | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 5000000 | 0 | 5000000
| Development of Mini-Parks Rotunda, Sta. Monica | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 20000000 | 0 | 20000000
| Installation of Underground Electrical Line and Power Supply, Sta. Monica | CED | NO | Competitive Bidding | 2021-08-20 | 2021-09-20 | 2021-09-12 | 2021-09-13 | GoP | 28000000 | 0 | 28000000
| Installation of Water System Distribution, Sta. Monica | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 3595000 | 0 | 3595000
| CSWD Residential Care Facilities Site Developemtn/Covered Pathways, Mangingisda | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 500000 | 0 | 500000
| Rehabilitation of Drainage System along Carandang Street, Manggahan | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 4620000 | 0 | 4620000
| Construction of Drainage System (Along Quezon Street from Barangay Hall to Juan Luna Street), Maligaya | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 1715000 | 0 | 1715000
| Construction of Drainage System at Employees Village (Cactus Road), Sta. Monica | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 1024000 | 0 | 1024000
| Construction of Drainage System Castro Road, San Pedro | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 2800000 | 0 | 2800000
| Construction of Drainage System at Fernandez Extension with sidewalk, Tanglaw | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 3551500 | 0 | 3551500
| Construction of Drainage System at Purok Kaakbayan (Marines Compound), Tiniguiban | CED | NO | Competitive Bidding | 2021-08-03 | 2021-08-23 | 2021-08-26 | 2021-08-27 | GoP | 19451000 | 0 | 19451000
| Construction of Batching Plant-Other Facilities, Sta. Lucia | CED | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-01-29 | 2021-02-01 | GoP | 9758432 | 0 | 9758432
5-02-99-990 | Emergency and Post Emergency Period Expenses Brought by Typhoon Odette | CMO | NO | NP-53.2 Emergency Cases | 2021-12-22 | 2021-12-22 | 2021-12-24 | 2021-12-24 | GoP | 250000000 | 250000000
-Nothing Follows-
| Total Approved Supplemental Budget by the Agency Head | [8 empty] | 1731717867 | 880059000 | 851658867
Prepared by:
HAZEL U. SALAZAR
| Administrative Officer IV (A.O. II) |  |  | As to Existence of Appropriation: |  |  |  |  | APPROVED:
| JOEY VINCENT P. RABANAL, REA |  |  | MARIA REGINA S. CANTILLO | [5 empty] | HON. LUCILO R. BAYRON
| Supervising Administrative Officer |  |  | City Budget Officer | [5 empty] | City Mayor
| Head, BAC Secretariat | [8 empty] | Head of the Procuring Entity
Reccomended for Approval by:
Engr. JOVENEE C. SAGUN, EnP.
City Planning and Development Coordinator
BAC Chairperson
| Engr. ALBERTO P. JIMENEZ | Mr. GEORGE G. VASQUEZ |  |  |  | Mr. RAUL MANUEL J. BLAS |  |  |  |  | Dr. DEAN L. PALANCA
| City Engineer | Assistant City Planning & Dev't. Officer |  |  |  | City Civil Registrar |  |  |  |  | Assistant City Health Officer
| BAC Vice-Chairperson | BAC Member |  |  |  | BAC Member |  |  |  |  | BAC Member