## Sheet1
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
For the Quarter Ending 12/31/2020
Agency : |  |  | CITY GOVERNMENT OF PUERTO PRINCESA
[7 empty] | Target Completion Date | Project Status |  | No. of Extensions, if any
|  |  |  | Total Cost |  | Date Started
Program or Project | [7 empty] | % of completion | Total Cost incurred to date
Remarks
1 |  | (BUB) CONSTRUCTION OF 2 UNITS HEALTH STATIONS WITH COMPLETE EQUIPMENT |  | 6100000 | 2016-01-01 |  | 2018-01-04 | 54.73 | 3338323.6 | 0
2 |  | (BUB) EMPOWERMENT OF BARANGAYS CHILDREN AND PROTECTION |  | 1000000 | 2016-01-01 |  | 2018-02-08 | 100 | 1000000 | 0
3 |  | (BUB) WALANG TAMBAY SA BARANGAY |  | 282684 | 2015-01-01 |  | 2018-01-24 | 100 | 282684 | 0
4 |  | (BUB) OUT OF SCHOOL YOUTH RESIDENTIAL PROGRAM (MODULE 4 AND 5) |  | 181818.18 | 2015-01-01 |  | 2018-01-24 | 100 | 181818.18 | 0
5 |  | (BUB) PAG-ASA YOUTH ASSOCIATION YOUTH DAY CELEBRATION |  | 140000 | 2015-01-01 |  | 2018-01-24 | 100 | 140000 | 0
6 |  | PAYMENT FOR TB DOTS PATIENT UNDER PFPR |  | 84000 | 2016-01-01 |  | 2018-01-25 | 60 | 50400 | 0
7 |  | (BUB) SMALL IRRIGATION PROJECT (BGY. TAGABINET) |  | 2000000 | 2016-01-01 |  | 2017-12-11 | 0 | 0 | 0
8 |  | (BUB) SMALL IRRIGATION PROJECT (BGY. STA. CRUZ) |  | 1000000 | 2016-01-01 |  | 2017-12-11 | 0 | 0 | 0
9 |  | (BUB) HAND TRACTOR PROJECT |  | 150000 | 2016-01-01 |  | 2017-12-11 | 100 | 150000 | 0
10 |  | (BUB) RICE THRESHER |  | 300000 | 2016-01-01 |  | 2017-12-11 | 100 | 300000 | 0
11 |  | (BUB) SEAWEED POST HARVEST FACILITY |  | 1000000 | 2016-01-01 |  | 2017-12-11 | 0 | 0 | 0
12 |  | (BUB) POWER TILLER |  | 300000 | 2016-01-01 |  | 2017-12-11 | 100 | 300000 | 0
13 |  | (BUB) CONTINUOUS CAPACITY BUILDING FOR PARENT EFFECTIVENESS SESSION (PES) AND DAY CARE WORKERS |  | 701000 | 2015-01-01 |  | 2018-01-12 | 97.33 | 701000 | 0
14 |  | (BUB) DUCK EGG PRODUCTION |  | 285000 | 2016-01-01 |  | 2018-01-04 | 100 | 285000 | 0
15 |  | (BUB) EDUCATIONAL ASSISTANCE FOR OUT OF SCHOOL YOUTHS (OSYS) AND PERSONS WITH DISABILITY (PWD) |  | 2000000 | 2015-01-01 |  | 2018-01-11 | 96 | 1920000 | 0
16 |  | (BUB) INTEGRATED COMMUNITY FOOD PRODUCTION FOR FISHERFOLK FAMILIES |  | 1400000 | 2016-01-01 |  | 2018-01-05 | 78.55 | 1099728.35 | 0
17 |  | (BUB) SMALL DIVERSION DAM |  | 1200000 | 2016-01-01 |  | 2018-01-05 | 0 | 0 | 0
18 |  | (BUB) LOBSTER/GREEN GROUPER/SEA CUCUMBER CULTURE |  | 600000 | 2016-01-01 |  | 2018-01-05 | 100 | 600000 | 0
19 |  | (BUB) SEAWEEDS FARMING |  | 500000 | 2016-01-01 |  | 2018-01-05 | 100 | 500000 | 0
20 |  | SOCIAL PENSION BENEFICIARIES (COMPLETED) |  | 8616000 | 2016-01-01 |  | 2018-01-11 | 100 | 8616000 | 0
21 |  | (COMPLETED) ADDITIONAL SOCIAL PENSION BENEFICIARIES (1ST AND 2ND QTR) |  | 9519000 | 2016-01-01 |  | 2018-01-11 | 100 | 9519000 | 0
22 |  | (BUB) MANGROVE & NIPA PLANTATION |  | 292424.24 | 2016-01-01 |  | 2018-01-22 | 0 | 0 | 0
23 |  | (BUB) BAMBOO FURNITURE MAKING OF PAYAO ON CALL HOUSE MAINTENANCE |  | 282684 | 2016-01-01 |  | 2018-01-24 | 100 | 282684 | 0
24 |  | (BUB) MULTI-CAB SPARE PARTS PROJECT |  | 495000 | 2017-01-01 |  | 2017-12-11 | 100 | 495000 | 0
25 |  | (BUB) ESTABLISHMENT OF FURNITURE SHOP |  | 300000 | 2016-01-01 |  | 2018-01-24 | 100 | 300000 | 0
26 |  | PPCITY COMMUNITY ECOLOGICAL MANAGEMENT INSTITUTE FOR GLOBAL ENVIRONMENT STRATEGIES "IGES" IN HAYAMA, KANAGAWA, JAPAN |  | 794561.51 | 2011-01-01 |  | 2018-03-28 | 86.95 | 690895.2 | 0
27 |  | AGRI-PINOY TRADING CENTER |  | 40000000 | 2016-01-01 |  | 2017-12-12 | 100 | 39999999.99 | 0
28 |  | CONSTRUCTION/REPAIR/RENOVATION/IMPROVEMENT OF 5 BHS IN PPC UNDER HFEP 2014 |  | 5000000 | 2015-01-01 |  | 2018-04-03 | 100 | 4902335.81 | 0
29 |  | LGU WINNER OF GAWAD PAMANA NG LAHI |  | 7000000 | 2018-01-22 |  | 2018-01-22 | 71.43 | 5000000 | 0
30 |  | CENTER FOR HEALTH AND DEVELOPMENT IV-B INTENDED FOR IMPLEMENTATION OF DETEC TB |  | 4763925 | 2013-01-01 |  | 2018-01-05 | 95.37 | 4543163.09 | 0
31 |  | (BUB) SWINE PRODUCTION (BREEDING AND FATTENING) |  | 690000 | 2014-01-01 |  | 2017-12-19 | 100 | 690000 | 0
32 |  | FOOD PROCESSING (AGRI-FARM PRODUCTS) KITCHEN INCUBATOR |  | 1701900 | 2014-01-01 |  | 2017-12-19 | 100 | 1701900 | 0
33 |  | (BUB) ORGANIC VEGETABLE PRODUCTION THRU GREENHOUSE TECHNOLOGY |  | 3301995.73 | 2014-01-01 |  | 2017-12-19 | 90.4 | 2984993.9 | 0
34 |  | (BUB) BAMBOO DEVELOPMENT AND PROCESSING PROJECT |  | 2500000 | 2014-12-01 |  | 2017-12-19 | 100 | 2500000 | 0
35 |  | PQMI REHABILITATION PROJECT |  | 15000000 | 2014-01-01 |  | 2017-12-19 | 100 | 15000000 | 0
36 |  | DEVELOPMENT OF RELOCATION SITE (AFFECTED FAMILIES OF THE AIRPORT EXPANSION PROJECT) |  | 34886515.26 | 2014-01-01 |  | 2017-12-21 | 85.41 | 29797644.77 | 0
37 |  | MDG FAMILY- BASED ACTIONS FOR CHILDREN AND THEIR ENVIRONMENT IN THE SLUMS (SDG-FACES) PROJECT |  | 260000 | 2014-01-01 |  | 2018-01-03 | 99.94 | 259850 | 0
38 |  | (BUB) SHELTERED WORKSHOP CENTER WITH TRAINING FOR PERSONS WITH DISABILITY |  | 2300000 | 2014-01-01 |  | 2018-01-05 | 100 | 2300000 | 0
39 |  | CONSTRUCTION OF NATIONAL CHILD DEVELOPMENT CENTER |  | 2300000 | 2014-01-01 |  | 2018-01-05 | 83.43 | 1918957.37 | 0
40 |  | (BUB) OUT OF SCHOOL YOUTH RESIDENTIAL PROGRAM MODULE 1, 2 & 3 |  | 181818.18 | 2015-01-01 |  | 2018-01-18 | 100 | 181818.18 | 0
41 |  | (BUB) NATIVE CHICKEN PRODUCTION AND DISPERSAL PROJECT |  | 4500000 | 2014-01-01 |  | 2018-01-25 | 100 | 4500000 | 0
42 |  | (BUB) LUBA CULTURE IN CAGE |  | 1000000 | 2016-01-01 |  | 2018-01-26 | 100 | 1000000 | 0
43 |  | (BUB) HANDICRAFTS TRAINING AND MANUFACTURING |  | 530000 | 2014-01-01 |  | 2018-04-19 | 99.68 | 530000 | 0
44 |  | (BUB) SELF-EMPLOYMENT ASSISTANCE KAUNLARAN (SEA-K) |  | 2505282.09 | 2015-01-01 |  | 2017-12-19 | 87.2 | 2202087.7 | 0
45 |  | (BUB) COMMUNAL IRRIGATION PROJECT (SUPPLEMENTARY) |  | 3500000 | 2015-01-01 |  | 2018-01-25 | 0 | 0 | 0
46 |  | (BUB) COMMUNAL IRRIGATION PROJECT |  | 300000 | 2015-01-01 |  | 2017-12-19 | 0 | 0 | 0
47 |  | (BUB) FINANCIAL ASSISTANCE TO EDUCATIONAL NEEDS OF INDIGENOUS PEOPLE (IP) YOUTH |  | 701000.99 | 2015-09-02 |  | 2018-01-04 | 100 | 701000.99 | 0
48 |  | SPECIAL LOCAL ROADS FUND (SLRF) |  | 6845219.94 | 2015-01-01 |  | 2018-01-05 | 100 | 6845219.94 | 0
49 |  | CITY LEADERSHIP AND GOVERNANCE PROGRAM (CLGP) |  | 300000 | 2015-01-01 |  | 2018-01-05 | 84 | 251197.31 | 0
50 |  | (BUB) PALAWAN ECOLOGICAL ADVENTURE TRAIL PROJECT |  | 787727.27 | 2015-01-01 |  | 2018-01-05 | 100 | 498803.03 | 0
51 |  | TULONG PANGHANAP-BUHAY SA ATING MGA DISADVANTAGED/DISPLACED WORKERS (TUPAD) PROGRAM |  | 2848000 | 2020-10-01 |  | 2018-05-18 | 99.66 | 2838400 | 0
52 |  | (BUB) CAPABILITY BUILDING (BCPC) |  | 300000 | 2015-01-01 |  | 2018-01-05 | 100 | 300000 | 0
53 |  | (BUB) GROUP HAND WASHING FACILITY FOR DAY CARE CENTERS |  | 4402000 | 2015-01-01 |  | 2018-01-05 | 99.81 | 4402000 | 0
54 |  | REHABILITATION OF PUERTO PRINCESA CITYS GOAT BREEDING FARM |  | 390000 | 2014-01-01 |  | 2018-01-25 | 100 | 390000 | 0
55 |  | SOUVENIR ITEMS MAKING AND SELLING |  | 273888 | 2018-10-01 |  | 2018-05-18 | 99.54 | 273888 | 0
56 |  | ANIMAL BITE |  | 228000 | 2016-01-01 |  | 2018-01-26 | 89 | 202950 | 0
57 |  | PUERTO PRINCESA CITY MANGO PROCESSING FACILITY AND MARKETING CENTER I-REAP (CIVIL WORKS) |  | 5446260.1 | 2017-01-01 |  | 2018-04-02 | 100 | 5446260.1 | 0
58 |  | MAOYON FLOATING RESTAURANT AND RIVER PICNIC RAFTING |  | 356758 | 2018-10-01 |  | 2018-05-18 | 100 | 356758 | 0
59 |  | SOLAR STREET LIGHTING PROJECT FOR BGY LANGOGAN, BGY BINDUYAN AND BGY KAMUNING, PUERTO PRINCESA CITY |  | 10000000 | 2020-06-25 |  | 2018-05-18 | 99.98 | 9124218.5 | 0
60 |  | BOAT SERVICES AND SNORKELING RENTALS |  | 500000 | 2018-10-01 |  | 2018-05-18 | 99 | 495048 | 0
61 |  | COMMUNITY BAKERY |  | 265465 | 2018-10-01 |  | 2018-05-18 | 100 | 265465 | 0
62 |  | WATER REFILLING STATION |  | 750000 | 2018-10-01 |  | 2018-05-18 | 100 | 750000 | 0
63 |  | HANDICRAFT MAKING AND T-SHIRT PRINTING |  | 259687.5 | 2018-10-01 |  | 2018-05-18 | 100 | 259687.5 | 0
64 |  | SURVIVAL T-SHIRT PRINTING AND SELLING |  | 231140 | 2018-10-01 |  | 2018-05-18 | 100 | 231140 | 0
65 |  | BEACH ACCESSORIES RENTALS |  | 515660 | 2018-10-01 |  | 2018-05-18 | 100 | 515660 | 0
66 |  | FLOATING RESTAURANT WITH SOUVENIR T-SHIRT PRODUCTION |  | 194340 | 2018-10-01 |  | 2018-05-18 | 99.48 | 194340 | 0
67 |  | CONSTRUCTION OF BAHAY PAG-ASA, BGY. MANGINGISDA, PUERTO PRINCESA CITY |  | 4944964.25 | 2018-12-11 |  | 2018-05-18 | 100 | 4944964.25 | 0
68 |  | PHOTO PRINT, T-SHIRT PRINTING AND MUG PRINTING |  | 499500 | 2018-10-01 |  | 2018-05-18 | 100 | 499500 | 0
69 |  | DRAINAGE IMPROVEMENT OF SARHENTO ST., KALYE SEKSI, KAAKBAYAN, BGY. TINIGUIBAN |  | 6709681 | 2018-11-22 |  | 2018-05-18 | 100 | 6709681 | 0
70 |  | ESTABLISHMENT OF BSMPMODAI MULTICAB SPARE PARTS STORE |  | 1000000 | 2018-10-01 |  | 2018-05-18 | 100 | 1000000 | 0
71 |  | FIBERGLASS FABRICATION AND BOAT BUILDING |  | 1000000 | 2018-10-01 |  | 2018-05-18 | 100 | 1000000 | 0
72 |  | DEVELOPMENT OF BALAYONG NATURE PARK |  | 86865534 | 2019-07-01 |  | 2018-05-18 | 82.23 | 71631593.91 | 0
73 |  | LIVESTOCK DISPERSAL OF WORKING ANIMALS CARABAO PROJECT |  | 1526790 | 2014-07-01 |  | 2018-05-18 | 100 | 1526790 | 0
74 |  | PHILHEALTH CAPITATION FUND |  | 1400000 | 2016-01-01 |  | 2018-05-18 | 93 | 1301997.6 | 0
75 |  | PRDP BUAL-BUALAN FARM TO MARKET ROAD |  | 31994449.71 | 2018-01-01 |  | 2018-01-22 | 100 | 31790333.92 | 0
76 |  | GRANT/SUBSIDY FOR THE BILLETING DEPED SCHOOLS IN FAVOR OF PPCITY |  | 465000 | 2019-09-01 |  | 2018-05-18 | 100 | 465000 | 0
77 |  | MOTORIZED FISHING BANCA WITH FISHING PARAPHERNALIA PROJECT |  | 1500000 | 2016-12-01 |  | 2018-05-18 | 100 | 1500000 | 0
78 |  | ESTABLISHMENT OF MATERIALS RECOVERY FACILITY (MRF) |  | 142500 | 2018-03-02 |  | 2018-05-18 | 100 | 142500 | 0
79 |  | SOCIAL AMELIORATION PROGRAM (SAP) |  | 184780000 | 2020-01-01 |  | 2018-05-18 | 100 | 184780000 | 0
80 |  | SOCIAL AMELIORATION PROGRAM (SAP) FOR PANTAWID PAMILYANG PILIPINO PROGRAM (4PS) BENEFICIARIES |  | 1354150 | 2020-05-11 |  | 2018-05-18 | 100 | 1354150 | 0
81 |  | PHOTO BOOTH AND BIKE RENTAL |  | 249000 | 2018-10-01 |  | 2018-05-18 | 100 | 249000 | 0
82 |  | MATCHING GRANT PROGRAM (MNCHN) |  | 1400000 | 2017-01-01 |  | 2018-01-22 | 96 | 1337965.88 | 0
83 |  | SM INVESTMENT CAP MANILA |  | 60000 | 2016-01-01 |  | 2018-03-27 | 73 | 43698.21 | 0
84 |  | FUND TRANSFER INTENDED FOR SURVEY OF SITIO TAGBARUNGIS, BGY. IWAHIG |  | 1900000 | 2016-01-01 |  | 2018-03-27 | 39.24 | 745600 | 0
85 |  | CONSTRUCTION OF BHS IN BGY. PRINCESA, SAN MIGUEL, MAUNLAD, BANCAO-BANCAO AND MATAHIMIK |  | 7462500 | 2016-01-01 |  | 2018-04-02 | 51.08 | 3811659.2 | 0
86 |  | YAMAN PINOY ECO BAG PRODUCTION |  | 500000 | 2016-01-01 |  | 2018-04-12 | 100 | 500000 | 0
87 |  | FINANCIAL ASSISTANCE FOR THE SERVICES OF 293 EXISTING AND 21 NEW BGY NUTRITION SCHOLARS |  | 187800 | 2016-01-01 |  | 2018-04-18 | 100 | 187800 | 0
88 |  | (BUB) ORGANIC HOG RAISING |  | 270000 | 2016-01-01 |  | 2018-04-20 | 100 | 270000 | 0
89 |  | (BUB) INTEGRATED COMMUNITY FOOD PRODUCTION |  | 2200000 | 2016-01-01 |  | 2018-04-20 | 44.29 | 974327 | 0
90 |  | (BUB) GILLNET FISHING WITH MOTORIZED BANCA |  | 1500000 | 2016-01-01 |  | 2018-04-24 | 100 | 1500000 | 0
91 |  | REGULATORY IMPACT ASSESSMENT PROJECT |  | 700065 | 2017-01-01 |  | 2018-03-27 | 0 | 0 | 0
92 |  | SUPPLEMENTARY FEEDING PROGRAM (7TH CYCLE) |  | 8406000 | 2017-06-01 |  | 2018-04-12 | 99.8 | 8406000 | 0
93 |  | SPONSORSHIP FOR THE RENOVATION OF VISITORS WAITING SHED |  | 90000 | 2017-01-01 |  | 2018-04-18 | 0 | 0 | 0
94 |  | PERFORMANCE CHALLENGE FUND (PCF) |  | 3400000 | 2017-01-01 |  | 2018-04-02 | 100 | 3400000 | 0
95 |  | PERFORMANCE CHALLENGE FUND (PCF) 2017 |  | 2400000 | 2017-01-01 |  | 2018-04-02 | 99.94 | 2398500 | 0
96 |  | SOCIAL PENSION FOR INDIGENT SENIOR CITIZENS |  | 13515000 | 2020-01-01 |  | 2018-05-18 | 82.35 | 11130000 | 0
97 |  | COMBINE HARVESTER |  | 480000 | 2016-01-01 |  | 2018-01-24 | 100 | 480000 | 0
98 |  | CORN PROGRAM- 4 WHEEL DRIVE TRACTOR |  | 750000 | 2016-01-01 |  | 2018-01-24 | 100 | 750000 | 0
99 |  | SUPPLEMENTARY FEEDING PROGRAM FOR SCHOOL CHILDREN FROM JOLLIBEE FOUNDATION |  | 11886 | 2013-01-01 |  | 2018-01-05 | 0 | 0 | 0
100 |  | PUERTO PRINCESA CITY MANGO PROCESSING FACILITY AND MARKETING CENTER I-REAP (ENTERPRISE) |  | 6711370.71 | 2017-01-01 |  | 2018-01-22 | 100 | 6711370.71 | 0
101 |  | (COMPLETED) SOCIAL PENSION BENEFICIARIES FOR 1ST AND 2ND QUARTER 2016 |  | 5319000 | 2016-01-01 |  | 2018-01-11 | 100 | 5319000 | 0
102 |  | T/F FOR TRAVELLING ALLOWANCE OF 318 EXISTING BNS FOR CY 2018 |  | 365400 | 2019-01-01 |  | 2018-05-18 | 99.53 | 363700 | 0
103 |  | BUREAU OF FIRE PROTECTION |  | 2868403.06 | 2017-01-01 |  | 2018-01-05 | 99.81 | 2862918 | 0
104 |  | (COMPLETED) SOCIAL PENSION BENEFICIARIES |  | 774000 | 2015-01-01 |  | 2018-05-18 | 100 | 774000 | 0
105 |  | CULTURE OF MARINE FISH IN FLOATING NET CAGES WITH FLOATING COTTAGES |  | 2000000 | 2014-01-01 |  | 2018-05-18 | 100 | 2000000 | 0
106 |  | CONSTRUCTION/REHABILITATION OF SABANG ROAD, SITIO SABANG, BGY. CABAYUGAN |  | 1000000 | 2013-01-01 |  | 2018-05-18 | 99.98 | 999830 | 0
107 |  | SOCIAL PENSION OF INDIGENT SENIOR CITIZENS (COMPLETED) |  | 74544000 | 2018-07-02 |  | 2018-05-18 | 100 | 74544000 | 0
108 |  | FINANCIAL ASSISTANCE TO PPSRNP LAYOUT AND PRINTING OF FIELD GUIDE BOOK |  | 180000 | 2017-01-01 |  | 2018-04-18 | 0 | 0 | 0
| TOTAL |  |  | 670767748.72 |  |  |  |  | 623513200.19
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CHARLITO B. PADUL |  |  |  |  | LUCILO R. BAYRON
City Accountant |  |  |  |  | Local Chief Executive