## Form 7 - DFU
FDP Form 7 - 20% COMPONENT OF THE IRA UTILIZATION
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
| REGION: |  | MIMAROPA |  |  | CALENDAR YEAR: | 2025
| PROVINCE: |  | PALAWAN |  |  | QUARTER: | 2
| CITY/MUNICIPALITY: |  | CITY OF PUERTO PRINCESA
Code | Program / Project |  |  |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extension, if any | Remarks
[9 empty] | % of | Total Cost
[9 empty] | Completion | Incurred to Date
ECONOMIC DEVELOPMENT
8918-1 | CONSTRUCTION OF NEW CITY CEMETERY PHASE VI, BRGY. STA. LOURDES
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | Sta. Lourdes | 30000000 | 2025-02-07 | 2025-08-05 | 43.24% | 4454736.78 |  | By contract
8918-2 | ROAD REBLOCKING WITH SLOPE PROTECTION OF MACARASCAS-SABANG ROAD (various brgys.)
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Various Brgys. | 20000000 | 2025-04-09 | 2026-03-04 | 43.03% |  |  | By contract
8918-3 | CONCRETING OF ROAD NETWORKS AT MEDINA RELOCATION SITE PHASE II, BRGY. SICSICAN | [10 empty] | Project physically
| 3.0 Capital Outlay | [10 empty] | completed
|  | Road Networks |  |  | Sicsican | 9947500 | 2025-02-13 | 2025-05-28 | 100% | 5582937.86 |  | By contract
8918-4 | CONCRETING OF ROAD NETWORKS AT PAGKAKAISA RELOCATION SITE PHASE III, BRGY. SICSICAN | [10 empty] | Project physically
| 3.0 Capital Outlay | [10 empty] | completed
|  | Road Networks |  |  | Sicsican | 8298715 | 2025-02-18 | 2025-05-18 | 100% | 3274420.74 |  | By contract
8918-5 | REPLACEMENT/ CONCRETING OF CIRCUMFERENTIAL ROAD (Liberty-Puloy to Roxas Street), Various Barangays
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Various Brgys. | 32377500 | 2025-02-18 | 2025-11-29 | 23.46% | 4812192.5 |  | By contract
8918-6 | CONCRETING OF PUROK MASAGANA FMR (Gabayan Road), BRGY. BAHILE
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Bahile | 15000000 | 2025-02-17 | 2025-08-01 | 54.49% |  |  | By contract
8918-7 | ROAD REBLOCKING OF FARM-TO MARKET ROAD FROM BUKANG LIWAYWAY TO MAKANDRING, BRGY. LANGOGAN
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Langogan | 15000000 | 2025-03-17 | 2025-10-12 | 18.39% | 1290 |  | By contract
8918-8 | CONCRETING OF FARM-TO-MARKET ROAD PHASE III, BRGY. MARUFINAS
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Marufinas | 18000000 | 2025-02-07 | 2025-10-04 | 93.8% | 11395621.03 |  | By contract
8918-9 | CONCRETING OF GK GOLDEN VALLEY ROAD NETWORKS AT PUROK MANGA, BRGY. SICSICAN
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Sicsican | 14964500 | 2025-02-13 | 2025-08-11 | 66.46% | 7261692.7 |  | By contract
8918-10 | CONSTRUCTION/CONCRETING OF CACATIAN ROAD (SEA BREEZE), BRGY. SAN JOSE
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | San Jose | 28776000 | 2025-02-07 | 2025-08-05 | 85.58% | 4272913.53 |  | By contract
8918-11 | CONCRETING OF CALACHUCHI STREET, BRGY. SAN MIGUEL
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | San Miguel | 3960000 | 2025-05-05 | 2025-08-17 | 55.13% | 3941522.22 |  | By admin
8918-12 | CONCRETING OF ROAD NETWORK AT PUROK TALISAY, BRGY. SICSICAN
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Sicsican | 14241500 | 2025-02-13 | 2025-08-11 | 50.86% |  |  | By contract
8918-13 | CONCRETING OF MCKINLEY HILLS DRIVE AT PUROK PAGKAKAISA, BRGY. STA. MONICA
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Sta. Monica | 20256500 | 2025-02-13 | 2025-07-12 | 80.51% | 2992717.36 |  | By contract
8918-14 | OPENING AND GRAVELLING OF ROAD LEADING TO PUROK UNANG LAHI, BRGY. STA. LOURDES
3.0 Capital Outlay
|  | Road Networks |  |  | Sta. Lourdes | 2895538 | [5 empty] | Unimplemented
8918-15 | REPLACEMENT/CONCRETING OF FERNANDEZ STREET, BRGY. TANGLAW
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Tanglaw | 18407200 | 2025-02-18 | 2025-10-30 | 43.54% | 2733435 |  | By contract
8918-16 | ROAD REBLOCKING OF PAGAYONA ROAD (Mass Way to Atis Road), BRGY. SAN MANUEL
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | San Manuel | 17608084 | 2025-06-03 | 2026-05-13 |  | 17482966.35 |  | By admin
8918-17 | ROAD REBLOCKING OF SANTOL ROAD (National Highway to Atis Road), BRGY. SAN JOSE
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | San Jose | 28068577 | 2025-06-11 | 2026-05-21 | 0.3% | 27844736.02 |  | By admin
8918-18 | ROAD REBLOCKING OF NADAYAO ROAD (National Highway to Abanico Road), BRGY. SAN PEDRO
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | San Pedrso | 19332568 |  |  |  | 19167437.43 |  | By admin
8918-19 | ROAD REBLOCKING OF VILLAROSA ROAD (Manalo Extension to Abueg Street), BRGY. BANCAO-BANCAO
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Bancao-Bancao | 10846877 |  |  |  | 10778852.96 |  | By admin
8918-20 | ROAD REBLOCKING OF BURGOS STREET (Manalo Street to Bonifacio Street), BRGY. MASIPAG
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Masipag | 11585878 |  |  |  | 11492225.11 |  | By admin
8918-21 | CONCRETING OF ROAD BESIDE HILLSIDE WITH DRAINAGE SYSTEM AT PUROK SANDIWA, BRGY. TINIGUIBAN
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | Tiniguiban | 9959000 | 2025-02-17 | 2025-08-30 | 48.24% | 1290 |  | By contract
8918-22 | CONCRETING OF KALAMANSI ROAD WITH SIDEWALK AND DRAINAGE SYSTEM, BRGY. SAN JOSE
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Road Networks |  |  | San Jose | 30690000 | 2025-02-13 | 2025-10-25 | 18.56% | 4543553.15 |  | By contract
8918-23 | CONCRETING OF ACCESS ROAD FROM PUROK MAGSASAKA TO MANGINGISDA CEMETERY, BRGY. MANGINGISDA | [10 empty] | Project physically
| 3.0 Capital Outlay | [10 empty] | completed
|  | Road Networks |  |  | Mangingisda | 20492500 | 2025-02-04 | 2025-06-18 | 100% | 12093238.51 |  | By contract
8918-24 | CONCRETING OF ACCESS ROAD FROM HIGHWAY TO TAGBARUNGIS ELEM. AND HIGH SCHOOL, BRGY. INAGAWAN SUB-COLONY
| 3.0 Capital Outlay |  |  |  | Inagawan | [6 empty] | Project on-going
|  | Road Networks |  |  | Sub-colony | 20978500 | 2025-02-07 | 2025-08-05 | 98.02% | 20070906.41 |  | By contract
8918-25 | ASPHALT OVERLAY OF MANALO STREET (Reynoso to Fernandez), Various Brgys.
| 3.0 Capital Outlay | [10 empty] | POW/DED
|  | Road Networks |  |  | Various Brgys. | 28468500 | [5 empty] | for revision
8918-26 | ASPHALT OVERLAY OF WESCOM Rd. (Sta. 1+466.80 to Sta. 2+769.10) BRGY. SAN MIGUEL
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Road Networks |  |  | San Miguel | 18411500 | 2025-03-25 | 2025-05-08 | 100% | 15330926.22 |  | By admin
8918-27 | CONSTRUCTION OF BUENAVISTA WHARF PHASE IV, BRGY. BUENAVISTA
| 3.0 Capital Outlay | [10 empty] | For CNC/ECC
|  | Seaport System |  |  | Buenavista | 32515000 | [5 empty] | application
8918-28 | CONSTRUCTION OF BAGONG BAYAN WHARF PHASE IV, BRGY. BAGONG BAYAN
| 3.0 Capital Outlay | [10 empty] | For CNC/ECC
|  | Seaport System |  |  | Bagong Bayan | 15621000 | [5 empty] | application
8918-29 | CONSTRUCTION OF BALAYONG FOOD PARK, BRGY. STA. MONICA
3.0 Capital Outlay
|  | Parks, Plazas and Monuments |  |  | Sta. Monica | 45388400 | [5 empty] | For bidding
8918-30 | IMPROVEMENT OF CITY COLISEUM FREEDOM PARK (Fence, Gate, Landscape, Public Toilet, Guard House, Maint. Bldg. & Interactive Fountain) BRGY. SAN PEDRO
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Parks, Plazas and Monuments |  |  | San Pedro | 73204344 | 2025-02-11 | 2025-12-07 | 0.43% | 10914168.45 |  | By contract
8918-31 | CONSTRUCTION OF PPC SKATE PARK AT BRGY. STA. MONICA
3.0 Capital Outlay
|  | Parks, Plazas and Monuments |  |  | Sta. Monica | 51000000 | [5 empty] | Unimplemented
8918-32 | EMBANKMENT/RECLAMATION OF COASTAL DEVELOPMENT PROJECT (Baywalk Area), BRGY. MATAHIMIK
3.0 Capital Outlay
|  | Other Infrastructure Assets |  |  | Matahimik | 25000000 | [5 empty] | Unimplemented
8918-33 | CONSTRUCTION OF MINI CITY HALL AT MACARASCAS RURAL SERVICE CENTER (RSC), BRGY. MACARASCAS
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Buildings |  |  | Macarascas | 29428523 | 2025-03-17 | 2026-03-16 | 21.35% |  |  | By contract
8918-34 | RENOVATION OF CITY COLISEUM BUILDING PHASE II, BRGY. SAN PEDRO
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Buildings |  |  | San Pedro | 120000000 | 2025-03-17 | 2026-03-16 | 2.11% | 17925515.39 |  | By contract
8918-35 | COMPLETION OF THE RENOVATION OF OLD TERMINAL BUILDING, BRGY. SAN JOSE
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Buildings |  |  | San Jose | 72010106 | 2025-03-17 | 2025-12-11 | 17.21% | 10757547.6 |  | By contract
8918-36 | COMPLETION OF SAN JOSE PUBLIC MARKET, BRGY. SAN JOSE
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Markets |  |  | San Jose | 32513000 | 2025-02-11 | 2025-06-10 | 15.5% | 4851309.1 |  | By contract
[6 empty] | 965247310 |  |  |  | 233978152.42
We hereby certify that we have reviewed the contents and hereby attest to | We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
the veracity and correctness of the data of information contained in this
document.
APPROVED:
|  | ENGR. ARIES S. GRANDE |  | REGINA S. CANTILLO
|  | Assistant City Engineer |  | City Budget Officer
|  | Officer In-charge | [6 empty] | LUCILO R. BAYRON
City Mayor