## 2023 20% IRA U. 1st Qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
for the 1st Quarter, CY 2023
City of Puerto Princesa
Program/ Project |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[7 empty] | % of Completion | Total Cost Incured to Date
ECONOMIC SERVICES
8918-3(23) | CONCRETING/COMPLETION OF PAGLAUM TO CEMETERY ROAD, BGY. MANGINGISDA
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Infrastructure Assets - Road Networks | Mangingisda | 8952645 | [5 empty] | For bidding
8918-4(23) | CONSTRUCTION OF DRAINAGE SYSTEM AT KALYE CUTE PHASE II, BGY. STA. MONICA
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Drainage and Slope Protection Structures | Sta. Monica | 11698200 | [5 empty] | POW
8918-5(23) | CONCRETING OF KAAKBAYAN ROAD NETWORKS WITH DRAINAGE SYSTEM PHASE II, BGY. TINIGUIBAN
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Road Networks | Tiniguiban | 35000000 | [5 empty] | POW
8918-6(23) | CONCRETING/COMPLETION OF RANCHERO ROAD (DIMALANTA TO RAMPANO), BGY. STA. LOURDES
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Road Networks | Sta. Lourdes | 11329650 | [5 empty] | POW
8918-8(23) | CONSTRUCTION OF ENGINEERING AND ARCHITECTURE BUILDING PHASE II, BGY. STA. MONICA
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Buildings & Other Structures - Buildings | Sta. Monica | 85000000 | [5 empty] | POW
8918-9(23) | UNDERGROUND CABLING OF BALAYONG PARK CIRCUIT PHASE II, BGY. STA. MONICA
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Power Supply Systems | Sta. Monica | 13446700 | [5 empty] | POW
8918-10(23) | CONCRETING/COMPLETION OF BUKANG-LIWAYWAY HOA ROAD WITH DRAINAGE SYSTEM, BGY.BANCAO-BANCAO
| 3.0 Capital Outlay | [8 empty] | WithABC
|  | Infrastructure Assets - Road Networks | Bancao-Bancao | 9357000 | [5 empty] | For bidding
8918-11(23) | COMPLETION OF CABAIRAN FOOTBRIDGE, BGY. MANALO
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Infrastructure Assets - Road Networks | Manalo | 4075000 | [5 empty] | Fior bidding
8918-13(23) | CONCRETING OF ZABALA ROAD WITH DRAINAGE SYSTEM BESIDE TINIGUIBAN ELEM. SCHOOL, BGY. TINIGUIBAN
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Infrastructure Assets - Road Networks | Tiniguiban | 5442675 | [5 empty] | For bidding
8918-14(23) | OPENING AND GRAVELLING OF OLD SANTOL ROAD, BGY. SAN JOSE
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Road Networks | San Jose | 5803135 | [5 empty] | POW
8918-15(23) | CONCRETING OF PADUGA ROAD FROM BAPTIST CHURCH TO REGINO ROAD (PUROK PAGKAKAISA), BGY. STA. MONICA
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Infrastructure Assets - Road Networks | Sta. Monica | 9485805 | [5 empty] | For bidding
8918-16(23) | CONCRETING OF MANGA ROAD (FULBRIGHT COLLEGE), BGY. SAN JOSE
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Infrastructure Assets - Road Networks | San Jose | 19282620 | [5 empty] | For bidding
8918-17(23) | SITE DEVELOPMENT OF IRAWAN AGRICULTURAL CENTER PHASE II (ROAD, PARKING, SIDEWALK AND DRAINAGE), BGY. IRAWAN
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Other Land Improvements | Irawan | 50000000 | [5 empty] | POW
8918-18(23) | REPLACEMENT/CONCRETING OF MITRA ROAD (BAKER'S HILL), BGY. STA. MONICA
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Infrastructure Assets - Road Networks | Sta. Monica | 95969000 | [5 empty] | For bidding
8918-19(23) | CONCRETING OF ACCESS ROAD TO VALDEZTAMON RELOCATION SITE, BGY. SICSICAN
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Road Networks | Sicsican | 10843000 | [5 empty] | POW
8918-22(23) | CONCRETING OF ROAD FROM PUROK KAUNLARAN TO PUROK KATIWASAYAN, BGY. LUZVIMINDA
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Infrastructure Assets - Road Networks | Luzviminda | 24549200 | [5 empty] | For bidding
8918-23(23) | CONSTRUCTION OF CITY CEMETERY PHASE IV, BGY. STA. LOURDES
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Other Land Improvements | Sta. Lourdes | 65474995.53 | [5 empty] | For bidding
8918-24(23) | CONSTRUCTION OF HANGING BRIDGE AT SITIO KALAKWASAN, BGY. TANABAG
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Road Networks | Tanabag | 7687500 | [5 empty] | POW
8918-25(23) | CONSTRUCTION OF HANGING BRIDGE AT SITIO TAGNAYA, BGY. CONCEPCION
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Road Networks | Concepcion | 7687500 | [5 empty] | POW
8918-26(23) | CONSTRUCTION OF HANGING BRIDGE AT SITIO MANGGAPIN, BGY. CONCEPCION
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Road Networks | Concepcion | 7687500 | [5 empty] | POW
8918-30(23) | PRINCESS EULALIA PARK LANDSCAPE AND PARKING, BGY. LIWANAG
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Other Land Improvements | Liwanag | 10000000 | [5 empty] | POW
8918-32-a(23) | ROAD REBLOCKING OF T.S.PAREDES ST. (former Abad Santos St.)
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks |  | 25449457.57 |  |  |  | 23607369.45 |  | For bidding
8918-32-b(23) | ROAD REBLOCKING OF FUNDADOR ROAD
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | San Miguel | 2182953.06 |  |  |  | 2017494.15 |  | For bidding
8918-32-c(23) | ROAD REBLOCKING OF LOMBOY ROAD
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | San Jose | 12187980.57 |  |  |  | 11292584.55 |  | For bidding
8918-32-d(23) | ROAD REBLOCKING OF MP ROAD
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | San Miguel | 2176825.86 |  |  |  | 2004299.55 |  | For bidding
8918-32-e(23) | ROAD REBLOCKING OF VALENCIA MANALO TO PAROLA ROAD
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | Masipag | 19257342.16 |  |  |  | 17855289.3 |  | For bidding
8918-32-f(23) | ROAD REBLOCKING OF LANZANAS, TARABIDAN, BM AND TANGAY ROAD
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | San Pedro | 15810414.01 |  |  |  | 14647042.95 |  | For bidding
8918-33-a(23) | ASPHALT OVERLAY OF CARANDANG STREET
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | Manggahan | 2067426.53 | [5 empty] | For bidding
8918-33-b(23) | ASPHALT OVERLAY OF CASTRO ROAD
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | San Pedro | 2314066.34 | [5 empty] | For bidding
8918-33-c(23) | ASPHALT OVERLAY OF LACAO STREET
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | Maningning | 8575573.89 | [5 empty] | For bidding
8918-33-d(23) | ASPHALT OVERLAY W/ GRANULAR BASE OF ENTRANCE AT BATCHING PLANT
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | Sta. Lucia | 1142778.67 | [5 empty] | For bidding
8918-33-e(23) | ASPHALT OVERLAY OF P. VICENTE STREET
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | San Miguel | 4957915.39 | [5 empty] | For bidding
8918-33-f(23) | ASPHALT OVERLAY OF SAN JUAN ROAD
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | San Miguel | 2811497.3 | [5 empty] | For bidding
8918-33-g(23) | ASPHALT OVERLAY OF SOLID ROAD
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | San Manuel | 7393596.94 | [5 empty] | For bidding
8918-33-h(23) | ASPHALT OVERLAY OF TARABIDAN ROAD
| 3.0 Capital Outlay | [8 empty] | With PR
|  | Infrastructure Assets - Road Networks | San Manuel | 4357667.18 | [5 empty] | For bidding
8918-7(23) | CONCRETING/COMPLETION OF PARALLEL RD. 3 TO PUROK KAPALARAN W/ RC BOX CULVERT, BGY. LUZVIMINDA
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Infrastructure Assets - Road Networks | Luzviminda | 17218250 | [5 empty] | For bidding
8918-12(23) | OPENING AND GRAVELLING OF FMR FROM PUROK 3 TO MARAMBUHAYA, BGY. KAMUNING
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Road Networks | Kamuning | 12230000 | [5 empty] | POW
EDUCATION, CULTURE, SPORTS & MANPOWER DEVELOPMENT
8918-31(23) | RENOVATION OF SINAGTALA DAY CARE CENTER, BGY. BAGONG SILANG
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | School Buildings | Bagong Silang | 518859 | [5 empty] | For bidding
GENERAL PUBLIC SERVICES
8918-20(23) | SITE DEVELOPMENT OF LUZVIMINDA MINI CITY HALL (ROAD, PARKING, SIDEWALK AND DRAINAGE), BGY. LUZVIMINDA
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Other Land Improvements | Luzviminda | 6465000 | [5 empty] | For bidding
8918-21(23) | SITE DEVELOPMENT OF SAN RAFAEL MINI CITY HALL (ROAD, PARKING, SIDEWALK AND DRAINAGE), BGY. SAN RAFAEL
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Other Land Improvements | San Rafael | 21360000 | [5 empty] | For bidding
8918-28(23) | CONSTRUCTION OF PNP BUILDING AT BGY. MACARASCAS
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Buildings & Other Structures - Buildings | Macarascas | 25000000 | [5 empty] | POW
8918-29(23) | CONSTRUCTION OF PNP BUILDING AT BGY. SAN RAFAEL
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Buildings & Other Structures - Buildings | San Rafael | 26000000 | [5 empty] | For bidding
HEALTH SERVICES
8918-27(23) | CONSTRUCTION OF HAZARDOUS/HOSPITAL WASTE FACILITY, BGY. STA. LOURDES
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Other Infrastructure Assets | Sta. Lourdes | 25000000 | [5 empty] | POW
8918-1(23) | COMPLETION OF DOH SATELLITE CLINIC, BGY. NAPSAN
| 3.0 Capital Outlay | [8 empty] | With ABC
|  | Hospitals and Health Centers | Napsan | 10800000 | [5 empty] | For bidding
SOCIAL WELFARE SERVICES
8918-2(23) | COMPLETION OF SENIOR CITIZEN AND CHILDREN'S PARK WITH MOVABLE PUPPET SHOW STAGE, BGY. STA. MONICA
| 3.0 Capital Outlay | [8 empty] | Updating of
|  | Infrastructure Assets - Parks, Plazas and Monuments | Sta Monica | 13000000 | [5 empty] | POW
|  | GRAND TOTAL |  | 767049730 |  |  |  | 71424079.95
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
APPROVED:
ENGR. ALBERTO P. JIMENEZ |  | REGINA S. CANTILLO
City Engineer/Vice Chairman |  | City Budget Officer
LUCILO R. BAYRON
City Mayor
City Management Information Services - "Hindi BUKAS kundi NGAYON!...."