## TF 2nd Qtr 2023
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
For the Quarter Ending 12/31/2022
REGION: |  |  | MIMAROPA |  |  | CALENDAR YEAR: |  | 2023
PROVINCE: |  |  | CITY OF PUERTO PRINCESA (CAPITAL) |  |  | QUARTER: |  | 1
CITY/MUNICIPALITY: |  |  | CITY OF PUERTO PRINCESA (Capital)
[7 empty] | Target Completion Date |  | Project Status |  | No. of Extensions, if any
|  |  |  | Total Cost |  | Date Started
Program or Project | [8 empty] | % of completion | Total Cost incurred to date |  | Remarks
1 |  | (BUB) CONSTRUCTION OF 2 UNITS HEALTH STATIONS WITH COMPLETE EQUIPMENT |  | 6100000 | 2016-01-01 |  | 2018-01-04 |  | 54.73 | 3338323.6 | 0
2 |  | (BUB) MANGROVE & NIPA PLANTATION |  | 292424.24 | 2016-01-01 |  | 2018-01-22 |  | 0 | 0 | 0
3 |  | (COMPLETED) ADDITIONAL SOCIAL PENSION BENEFICIARIES (1ST AND 2ND QTR) |  | 9519000 | 2016-01-01 |  | 2018-01-11 |  | 100 | 9519000 | 0
4 |  | SOCIAL PENSION BENEFICIARIES (COMPLETED) |  | 8616000 | 2016-01-01 |  | 2018-01-11 |  | 100 | 8616000 | 0
5 |  | (BUB) SEAWEEDS FARMING |  | 500000 | 2016-01-01 |  | 2018-01-05 |  | 100 | 500000 | 0
6 |  | (BUB) LOBSTER/GREEN GROUPER/SEA CUCUMBER CULTURE |  | 600000 | 2016-01-01 |  | 2018-01-05 |  | 100 | 600000 | 0
7 |  | FINANCIAL ASSISTANCE TO PPSRNP LAYOUT AND PRINTING OF FIELD GUIDE BOOK |  | 180000 | 2017-01-01 |  | 2018-04-18 |  | 0 | 0 | 0
8 |  | (BUB) INTEGRATED COMMUNITY FOOD PRODUCTION FOR FISHERFOLK FAMILIES |  | 1400000 | 2016-01-01 |  | 2018-01-05 |  | 100 | 1400000 | 0
9 |  | (BUB) ESTABLISHMENT OF FURNITURE SHOP |  | 300000 | 2016-01-01 |  | 2018-01-24 |  | 100 | 300000 | 0
10 |  | (BUB) DUCK EGG PRODUCTION |  | 285000 | 2016-01-01 |  | 2018-01-04 |  | 100 | 285000 | 0
11 |  | AGRI-PINOY TRADING CENTER |  | 40000000 | 2016-01-01 |  | 2017-12-12 |  | 100 | 39999999.99 | 0
12 |  | (BUB) POWER TILLER |  | 300000 | 2016-01-01 |  | 2017-12-11 |  | 100 | 300000 | 0
13 |  | (BUB) SEAWEED POST HARVEST FACILITY |  | 1000000 | 2016-01-01 |  | 2017-12-11 |  | 100 | 1000000 | 0
14 |  | (BUB) RICE THRESHER |  | 300000 | 2016-01-01 |  | 2017-12-11 |  | 100 | 300000 | 0
15 |  | (BUB) HAND TRACTOR PROJECT |  | 150000 | 2016-01-01 |  | 2017-12-11 |  | 100 | 150000 | 0
16 |  | (BUB) SMALL DIVERSION DAM |  | 1200000 | 2016-01-01 |  | 2018-01-05 |  | 0 | 0 | 0
17 |  | CONSTRUCTION OF BHS IN BGY. PRINCESA, SAN MIGUEL, MAUNLAD, BANCAO-BANCAO AND MATAHIMIK |  | 7462500 | 2016-01-01 |  | 2018-04-02 |  | 100 | 6716250 | 0
18 |  | PPCITY COMMUNITY ECOLOGICAL MANAGEMENT INSTITUTE FOR GLOBAL ENVIRONMENT STRATEGIES "IGES" IN HAYAMA, KANAGAWA, JAPAN |  | 794561.51 | 2011-01-01 |  | 2018-03-28 |  | 86.95 | 690895.2 | 0
19 |  | SUPPLEMENTARY FEEDING PROGRAM (7TH CYCLE) |  | 8406000 | 2017-06-01 |  | 2018-04-12 |  | 100 | 8406000 | 0
20 |  | REGULATORY IMPACT ASSESSMENT PROJECT |  | 700065 | 2017-01-01 |  | 2018-03-27 |  | 0 | 0 | 0
21 |  | (BUB) GILLNET FISHING WITH MOTORIZED BANCA |  | 1500000 | 2016-01-01 |  | 2018-04-24 |  | 100 | 1500000 | 0
22 |  | (BUB) INTEGRATED COMMUNITY FOOD PRODUCTION |  | 2200000 | 2016-01-01 |  | 2018-04-20 |  | 100 | 2200000 | 0
23 |  | (BUB) ORGANIC HOG RAISING |  | 270000 | 2016-01-01 |  | 2018-04-20 |  | 100 | 270000 | 0
24 |  | (BUB) BAMBOO FURNITURE MAKING OF PAYAO ON CALL HOUSE MAINTENANCE |  | 282684 | 2016-01-01 |  | 2018-01-24 |  | 100 | 282684 | 0
25 |  | YAMAN PINOY ECO BAG PRODUCTION |  | 500000 | 2016-01-01 |  | 2018-04-12 |  | 87.54 | 500000 | 0
26 |  | (BUB) MULTI-CAB SPARE PARTS PROJECT |  | 495000 | 2017-01-01 |  | 2017-12-11 |  | 100 | 495000 | 0
27 |  | FUND TRANSFER INTENDED FOR SURVEY OF SITIO TAGBARUNGIS, BGY. IWAHIG |  | 1900000 | 2016-01-01 |  | 2018-03-27 |  | 39.24 | 1900000 | 0
28 |  | SM INVESTMENT CAP MANILA |  | 60000 | 2016-01-01 |  | 2018-03-27 |  | 73 | 43698.21 | 0
29 |  | (BUB) LUBA CULTURE IN CAGE |  | 1000000 | 2016-01-01 |  | 2018-01-26 |  | 100 | 1000000 | 0
30 |  | (BUB) EMPOWERMENT OF BARANGAYS CHILDREN AND PROTECTION |  | 1000000 | 2016-01-01 |  | 2018-02-08 |  | 100 | 1000000 | 0
31 |  | ANIMAL BITE |  | 228000 | 2016-01-01 |  | 2018-01-26 |  | 89 | 202950 | 0
32 |  | PAYMENT FOR TB DOTS PATIENT UNDER PFPR |  | 84000 | 2016-01-01 |  | 2018-01-25 |  | 60 | 50400 | 0
33 |  | FINANCIAL ASSISTANCE FOR THE SERVICES OF 293 EXISTING AND 21 NEW BGY NUTRITION SCHOLARS |  | 187800 | 2016-01-01 |  | 2018-04-18 |  | 100 | 187800 | 0
34 |  | PQMI REHABILITATION PROJECT |  | 15000000 | 2014-01-01 |  | 2017-12-19 |  | 100 | 15000000 | 0
35 |  | (BUB) SMALL IRRIGATION PROJECT (BGY. STA. CRUZ) |  | 1000000 | 2016-01-01 |  | 2017-12-11 |  | 100 | 1000000 | 0
36 |  | CLUSTERED SATELLITE CLINICS |  | 5000000 | 2015-01-01 |  | 2018-04-03 |  | 100 | 5000000 | 0
37 |  | (BUB) NATIVE CHICKEN PRODUCTION AND DISPERSAL PROJECT |  | 4500000 | 2014-01-01 |  | 2018-01-25 |  | 100 | 4500000 | 0
38 |  | REHABILITATION OF PUERTO PRINCESA CITYS GOAT BREEDING FARM |  | 390000 | 2014-01-01 |  | 2018-01-25 |  | 100 | 390000 | 0
39 |  | CONSTRUCTION OF NATIONAL CHILD DEVELOPMENT CENTER |  | 2300000 | 2014-01-01 |  | 2018-01-05 |  | 83.43 | 1918957.37 | 0
40 |  | (BUB) SHELTERED WORKSHOP CENTER WITH TRAINING FOR PERSONS WITH DISABILITY |  | 2300000 | 2014-01-01 |  | 2018-01-05 |  | 100 | 2300000 | 0
41 |  | (BUB) SELF-EMPLOYMENT ASSISTANCE KAUNLARAN (SEA-K) |  | 2505282.09 | 2015-01-01 |  | 2017-12-19 |  | 100 | 2505281.7 | 0
42 |  | DEVELOPMENT OF RELOCATION SITE (AFFECTED FAMILIES OF THE AIRPORT EXPANSION PROJECT) |  | 34886515.26 | 2014-01-01 |  | 2017-12-21 |  | 85.27 | 29749026.98 | 0
43 |  | (BUB) COMMUNAL IRRIGATION PROJECT (SUPPLEMENTARY) |  | 3500000 | 2015-01-01 |  | 2018-01-25 |  | 100 | 3500000 | 0
44 |  | (BUB) BAMBOO DEVELOPMENT AND PROCESSING PROJECT |  | 2500000 | 2014-12-01 |  | 2017-12-19 |  | 100 | 2500000 | 0
45 |  | (BUB) ORGANIC VEGETABLE PRODUCTION THRU GREENHOUSE TECHNOLOGY |  | 3301995.73 | 2014-01-01 |  | 2017-12-19 |  | 90.4 | 3301995.73 | 0
46 |  | FOOD PROCESSING (AGRI-FARM PRODUCTS) KITCHEN INCUBATOR |  | 1701900 | 2014-01-01 |  | 2017-12-19 |  | 100 | 1701900 | 0
47 |  | (BUB) SWINE PRODUCTION (BREEDING AND FATTENING) |  | 690000 | 2014-01-01 |  | 2017-12-19 |  | 100 | 690000 | 0
48 |  | CENTER FOR HEALTH AND DEVELOPMENT IV-B INTENDED FOR IMPLEMENTATION OF DETEC TB |  | 4763925 | 2013-01-01 |  | 2018-01-05 |  | 100 | 4763925 | 0
49 |  | LGU WINNER OF GAWAD PAMANA NG LAHI |  | 7000000 | 2018-01-22 |  | 2018-01-22 |  | 100 | 7000000 | 0
50 |  | MDG FAMILY- BASED ACTIONS FOR CHILDREN AND THEIR ENVIRONMENT IN THE SLUMS (SDG-FACES) PROJECT |  | 260000 | 2014-01-01 |  | 2018-01-03 |  | 100 | 260000 | 0
51 |  | (BUB) CAPABILITY BUILDING (BCPC) |  | 300000 | 2015-01-01 |  | 2018-01-05 |  | 100 | 300000 | 0
52 |  | PERFORMANCE CHALLENGE FUND (PCF) 2017 |  | 2400000 | 2017-01-01 |  | 2018-04-02 |  | 99.94 | 2400000 | 0
53 |  | (BUB) PAG-ASA YOUTH ASSOCIATION YOUTH DAY CELEBRATION |  | 140000 | 2015-01-01 |  | 2018-01-24 |  | 100 | 140000 | 0
54 |  | (BUB) OUT OF SCHOOL YOUTH RESIDENTIAL PROGRAM (MODULE 4 AND 5) |  | 181818.18 | 2015-01-01 |  | 2018-01-24 |  | 100 | 181818.18 | 0
55 |  | (BUB) WALANG TAMBAY SA BARANGAY |  | 282684 | 2015-01-01 |  | 2018-01-24 |  | 100 | 282684 | 0
56 |  | (BUB) OUT OF SCHOOL YOUTH RESIDENTIAL PROGRAM MODULE 1, 2 & 3 |  | 181818.18 | 2015-01-01 |  | 2018-01-18 |  | 100 | 181818.18 | 0
57 |  | (BUB) CONTINUOUS CAPACITY BUILDING FOR PARENT EFFECTIVENESS SESSION (PES) AND DAY CARE WORKERS |  | 701000 | 2015-01-01 |  | 2018-01-12 |  | 100 | 701000 | 0
58 |  | (BUB) HANDICRAFTS TRAINING AND MANUFACTURING |  | 530000 | 2014-01-01 |  | 2018-04-19 |  | 100 | 530000 | 0
59 |  | (BUB) GROUP HAND WASHING FACILITY FOR DAY CARE CENTERS |  | 4402000 | 2015-01-01 |  | 2018-01-05 |  | 100 | 4401999.6 | 0
60 |  | (BUB) SMALL IRRIGATION PROJECT (BGY. TAGABINET) |  | 2000000 | 2016-01-01 |  | 2017-12-11 |  | 100 | 2000000 | 0
61 |  | TULONG PANGHANAP-BUHAY SA ATING MGA DISADVANTAGED/DISPLACED WORKERS (TUPAD) PROGRAM |  | 2848000 | 2020-10-01 |  | 2018-05-18 |  | 100 | 2848000 | 0
62 |  | (BUB) PALAWAN ECOLOGICAL ADVENTURE TRAIL PROJECT |  | 787727.27 | 2015-01-01 |  | 2018-01-05 |  | 100 | 787727.27 | 0
63 |  | CITY LEADERSHIP AND GOVERNANCE PROGRAM (CLGP) |  | 300000 | 2015-01-01 |  | 2018-01-05 |  | 100 | 300000 | 0
64 |  | SPECIAL LOCAL ROADS FUND (SLRF) |  | 6845219.94 | 2015-01-01 |  | 2018-01-05 |  | 100 | 6845219.94 | 0
65 |  | (BUB) FINANCIAL ASSISTANCE TO EDUCATIONAL NEEDS OF INDIGENOUS PEOPLE (IP) YOUTH |  | 701000.99 | 2015-09-02 |  | 2018-01-04 |  | 100 | 701000.99 | 0
66 |  | (BUB) COMMUNAL IRRIGATION PROJECT |  | 300000 | 2015-01-01 |  | 2017-12-19 |  | 100 | 300000 | 0
67 |  | (BUB) EDUCATIONAL ASSISTANCE FOR OUT OF SCHOOL YOUTHS (OSYS) AND PERSONS WITH DISABILITY (PWD) |  | 2000000 | 2015-01-01 |  | 2018-01-11 |  | 96 | 2000000 | 0
68 |  | MOTORIZED FISHING BANCA WITH FISHING PARAPHERNALIA PROJECT |  | 1500000 | 2016-12-01 |  | 2018-05-18 |  | 100 | 1500000 | 0
69 |  | MOTIVATIONAL INCENTIVES/ AWARDS (MR - POLIO SIA 2020) |  | 170000 | 2020-12-10 |  | 2018-05-18 |  | 100 | 170000 | 0
70 |  | DEVELOPMENT OF MINI PARKS (CASCADING PARK, FRIENDSHIP PARK, PSU GATEWAY PARK AND ROTONDA PARK) |  | 16762351 | 2021-01-15 |  | 2018-05-18 |  | 97.53 | 16749204.48 | 0
71 |  | COVID-19 VACCINATION AND DEPLOYMENT |  | 4500000 | 2021-09-01 |  | 2018-05-18 |  | 100 | 4500000 | 0
72 |  | SOCIAL PENSION FOR INDIGENT SENIOR CITIZENS |  | 13515000 | 2020-01-01 |  | 2018-05-18 |  | 100 | 13515000 | 0
73 |  | SOCIAL AMELIORATION PROGRAM (SAP) FOR PANTAWID PAMILYANG PILIPINO PROGRAM (4PS) BENEFICIARIES |  | 1354150 | 2020-05-11 |  | 2018-05-18 |  | 100 | 1354150 | 0
74 |  | SPONSORSHIP FOR THE RENOVATION OF VISITORS WAITING SHED |  | 90000 | 2017-01-01 |  | 2018-04-18 |  | 0 | 0 | 0
75 |  | ESTABLISHMENT OF MATERIALS RECOVERY FACILITY (MRF) |  | 142500 | 2018-03-02 |  | 2018-05-18 |  | 0 | 142500 | 0
76 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - NATIONAL HOUSING AUTHORITY |  | 6250000 | 2021-12-01 |  | 2018-05-18 |  | 100 | 6250000 | 0
77 |  | GRANT/SUBSIDY FOR THE BILLETING DEPED SCHOOLS IN FAVOR OF PPCITY |  | 465000 | 2019-09-01 |  | 2018-05-18 |  | 100 | 465000 | 0
78 |  | PRDP BUAL-BUALAN FARM TO MARKET ROAD |  | 31994449.71 | 2018-01-01 |  | 2018-01-22 |  | 100 | 31994449.71 | 0
79 |  | PHILHEALTH CAPITATION FUND |  | 1400000 | 2016-01-01 |  | 2018-05-18 |  | 93 | 1301997.6 | 0
80 |  | LIVESTOCK DISPERSAL OF WORKING ANIMALS CARABAO PROJECT |  | 1526790 | 2014-07-01 |  | 2018-05-18 |  | 100 | 1526790 | 0
81 |  | DEVELOPMENT OF BALAYONG NATURE PARK |  | 86865534 | 2019-07-01 |  | 2018-05-18 |  | 98.56 | 86834451.4 | 0
82 |  | RECREATIONAL PARK WITH GREEN PARKING SPACE |  | 20857070 | 2021-01-01 |  | 2018-05-18 |  | 95.87 | 19995201.25 | 0
83 |  | SOCIAL AMELIORATION PROGRAM (SAP) |  | 184780000 | 2020-01-01 |  | 2018-05-18 |  | 100 | 184780000 | 0
84 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - PHILIPPINE CHARITY SWEEPSTAKES OFFICE (PCSO) |  | 2000000 | 2022-01-01 |  | 2018-05-18 |  | 100 | 2000000 | 0
85 |  | ONE COVID-19 ALLOWANCE (OCA) |  | 49316968.75 | 2022-01-01 |  | 2018-05-18 |  | 99.78 | 49207975 | 0
86 |  | UHC - HEALTH PROMOTION PLAYBOOK NO. 3 FOR IMMUNIZATION PROGRAM "BAKUNA CHAMPIONS" |  | 611821.86 | 2022-08-01 |  | 2018-05-18 |  | 94.36 | 577316.55 | 0
87 |  | INFORMATION SYSTEM ON TRANSPORT OPERATION IN PUERTO PRINCESA (ISTOPP) |  | 7500000 | 2022-11-01 |  | 2018-05-18 |  | 67.35 | 5051000 | 0
88 |  | ENHANCED KADIWA NI ANI AT KITA PROGRAM |  | 2300000 | 2022-05-17 |  | 2018-05-18 |  | 100 | 2300000 | 0
89 |  | INSTALLATION OF SOLAR STREET LIGHTS IN BGY. BACUNGAN AND BGY. STA. LOURDES |  | 20000000 | 2022-05-27 |  | 2018-05-18 |  | 90.8 | 18159410.16 | 0
90 |  | REGULAR AND TOP-UP FIXED TRANCHE FOR UHC IS 2022 |  | 1691360 | 2022-06-14 |  | 2018-05-18 |  | 100 | 1691360 | 0
91 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - BANGKO SENTRAL-LUCENA CITY |  | 20500 | 2021-12-01 |  | 2018-05-18 |  | 100 | 20500 | 0
92 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - CDRRM ZAMBOANGA CITY |  | 650000 | 2022-01-01 |  | 2018-05-18 |  | 100 | 650000 | 0
93 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - LAND BANK OF THE PHILIPPINES PUERTO PRINCESA BRANCH |  | 150000 | 2021-12-01 |  | 2018-05-18 |  | 100 | 150000 | 0
94 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - DEVELOPMENT BANK OF THE PHILIPPINES (DBP) - PUERTO PRINCESA CITY |  | 150000 | 2022-01-01 |  | 2018-05-18 |  | 0 | 0 | 0
95 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - MUNICIPALITY OF INFANTA, QUEZON |  | 100000 | 2022-01-01 |  | 2018-05-18 |  | 0 | 0 | 0
96 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - VIVANT FOUNDATION INC. |  | 350000 | 2021-12-01 |  | 2018-05-18 |  | 45.86 | 160500 | 0
97 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - HON. SARA DUTERTE- CARPIO |  | 500000 | 2021-12-01 |  | 2018-05-18 |  | 100 | 500000 | 0
98 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - PROVINCIAL GOVERNMENT OF DAVAO OCCIDENTAL |  | 1000000 | 2021-12-01 |  | 2018-05-18 |  | 100 | 1000000 | 0
99 |  | ESTABLISHMENT OF BSMPMODAI MULTICAB SPARE PARTS STORE |  | 1000000 | 2018-10-01 |  | 2018-05-18 |  | 100 | 1000000 | 0
100 |  | FINANCIAL ASSISTANCE FOR VICTIMS AFFECTED BY TYPHOON ODETTE (DONATION) - DRRMC/ LGU-BAGGAO, CAGAYAN VALLEY |  | 100000 | 2022-02-01 |  | 2018-05-18 |  | 33.93 | 33926.3 | 0
101 |  | T/F FOR TRAVELLING ALLOWANCE OF 318 EXISTING BNS FOR CY 2018 |  | 365400 | 2019-01-01 |  | 2018-05-18 |  | 100 | 365400 | 0
102 |  | COVID-19 SPECIAL RISK ALLOWANCE |  | 5487954.55 | 2021-01-01 |  | 2018-05-18 |  | 100 | 5487954.55 | 0
103 |  | CONSTRUCTION OF BAHAY PAG-ASA, BGY. MANGINGISDA, PUERTO PRINCESA CITY |  | 4944964.25 | 2018-12-11 |  | 2018-05-18 |  | 100 | 4944964.25 | 0
104 |  | DRAINAGE IMPROVEMENT OF SARHENTO ST., KALYE SEKSI, KAAKBAYAN, BGY. TINIGUIBAN |  | 6709681 | 2018-11-22 |  | 2018-05-18 |  | 100 | 6709681 | 0
105 |  | SOCIAL PENSION OF INDIGENT SENIOR CITIZENS (COMPLETED) |  | 74544000 | 2018-07-02 |  | 2018-05-18 |  | 100 | 74544000 | 0
106 |  | CONSTRUCTION/REHABILITATION OF SABANG ROAD, SITIO SABANG, BGY. CABAYUGAN |  | 1000000 | 2013-01-01 |  | 2018-05-18 |  | 99.98 | 999830 | 0
107 |  | CULTURE OF MARINE FISH IN FLOATING NET CAGES WITH FLOATING COTTAGES |  | 2000000 | 2014-01-01 |  | 2018-05-18 |  | 100 | 2000000 | 0
108 |  | PUERTO PRINCESA CITY MANGO PROCESSING FACILITY AND MARKETING CENTER I-REAP (CIVIL WORKS) |  | 5446260.1 | 2017-01-01 |  | 2018-04-02 |  | 100 | 5446260.1 | 0
109 |  | BUREAU OF FIRE PROTECTION |  | 2868403.06 | 2017-01-01 |  | 2018-01-05 |  | 98.87 | 2854575.57 | 0
110 |  | MAOYON FLOATING RESTAURANT AND RIVER PICNIC RAFTING |  | 356758 | 2018-10-01 |  | 2018-05-18 |  | 100 | 356758 | 0
111 |  | (COMPLETED) SOCIAL PENSION BENEFICIARIES FOR 1ST AND 2ND QUARTER 2016 |  | 5319000 | 2016-01-01 |  | 2018-01-11 |  | 100 | 5319000 | 0
112 |  | PUERTO PRINCESA CITY MANGO PROCESSING FACILITY AND MARKETING CENTER I-REAP (ENTERPRISE) |  | 6711370.71 | 2017-01-01 |  | 2018-01-22 |  | 100 | 6711370.71 | 0
113 |  | SUPPLEMENTARY FEEDING PROGRAM FOR SCHOOL CHILDREN FROM JOLLIBEE FOUNDATION |  | 11886 | 2013-01-01 |  | 2018-01-05 |  | 0 | 0 | 0
114 |  | CORN PROGRAM- 4 WHEEL DRIVE TRACTOR |  | 750000 | 2016-01-01 |  | 2018-01-24 |  | 100 | 750000 | 0
115 |  | COMBINE HARVESTER |  | 480000 | 2016-01-01 |  | 2018-01-24 |  | 100 | 480000 | 0
116 |  | MATCHING GRANT PROGRAM (MNCHN) |  | 464418.43 | 2017-01-01 |  | 2018-01-22 |  | 100 | 464418.43 | 0
117 |  | (COMPLETED) SOCIAL PENSION BENEFICIARIES |  | 774000 | 2015-01-01 |  | 2018-05-18 |  | 100 | 774000 | 0
118 |  | WATER REFILLING STATION |  | 750000 | 2018-10-01 |  | 2018-05-18 |  | 100 | 750000 | 0
119 |  | SOCIAL PENSION PROGRAM |  | 70812000 | 2023-01-01 |  | 2018-05-18 |  | 100 | 70812000 | 0
120 |  | SOUVENIR ITEMS MAKING AND SELLING |  | 273888 | 2018-10-01 |  | 2018-05-18 |  | 100 | 273888 | 0
121 |  | PHOTO PRINT, T-SHIRT PRINTING AND MUG PRINTING |  | 499500 | 2018-10-01 |  | 2018-05-18 |  | 100 | 499500 | 0
122 |  | PHOTO BOOTH AND BIKE RENTAL |  | 249000 | 2018-10-01 |  | 2018-05-18 |  | 100 | 249000 | 0
123 |  | FLOATING RESTAURANT WITH SOUVENIR T-SHIRT PRODUCTION |  | 194340 | 2018-10-01 |  | 2018-05-18 |  | 100 | 194340 | 0
124 |  | BEACH ACCESSORIES RENTALS |  | 515660 | 2018-10-01 |  | 2018-05-18 |  | 100 | 515660 | 0
125 |  | PERFORMANCE CHALLENGE FUND (PCF) |  | 3400000 | 2017-01-01 |  | 2018-04-02 |  | 100 | 3400000 | 0
126 |  | HANDICRAFT MAKING AND T-SHIRT PRINTING |  | 259687.5 | 2018-10-01 |  | 2018-05-18 |  | 100 | 259687.5 | 0
127 |  | FIBERGLASS FABRICATION AND BOAT BUILDING |  | 1000000 | 2018-10-01 |  | 2018-05-18 |  | 100 | 1000000 | 0
128 |  | COMMUNITY BAKERY |  | 265465 | 2018-10-01 |  | 2018-05-18 |  | 100 | 265465 | 0
129 |  | BOAT SERVICES AND SNORKELING RENTALS |  | 500000 | 2018-10-01 |  | 2018-05-18 |  | 100 | 500000 | 0
130 |  | FIXED TRANCHE FOR ANNUAL OPERATIONAL PLAN CY 2021 (COVID-19 RESPONSE AND UHC IS) |  | 1663429 | 2021-09-01 |  | 2018-05-18 |  | 100 | 1663429 | 0
131 |  | INSTALLATION OF SOLAR STREET LIGHTS IN RURAL AREAS |  | 10000000 | 2021-08-01 |  | 2018-05-18 |  | 99.89 | 9989072.8 | 0
132 |  | SPECIAL RISK ALLOWANCE (SRA) AND ACTIVE HAZARD DUTY PAY (AHDP) |  | 7300000 | 2021-01-01 |  | 2018-05-18 |  | 100 | 7300000 | 0
133 |  | SOLAR STREET LIGHTING PROJECT FOR BGY LANGOGAN, BGY BINDUYAN AND BGY KAMUNING, PUERTO PRINCESA CITY |  | 10000000 | 2020-06-25 |  | 2018-05-18 |  | 100 | 10000000 | 0
134 |  | SURVIVAL T-SHIRT PRINTING AND SELLING |  | 231140 | 2018-10-01 |  | 2018-05-18 |  | 100 | 231140 | 0
135 |  | BARANGAY NUTRITION SCHOLAR (BNS) |  | 390400 | 2022-07-12 |  | 2022-12-31 |  | 98.05 | 382800 | 0
136 |  | FINANCIAL ASSISTANCE TO LGUS AFFECTED BY |  | 16423361 | 2021-12-24 |  | 2022-03-31 |  | 100 | 16423361 | 0
TYPHOON ODETTE (SARO-LGRCB-21-0013737)
137 |  | FINANCIAL ASSISTANCE TO LGUS AFFECTED BY |  | 15094853 | 2021-12-28 |  | 2022-03-31 |  | 100 | 15094853 | 0
TYPHOON ODETTE (SARO-LGRCB-21-0013791)
138 |  | FINANCIAL ASSISTANCE TO LGUS AFFECTED BY |  | 81736000 | 2021-12-29 |  | 2022-03-31 |  | 100 | 81736000 | 0
TYPHOON ODETTE (SARO-LGRCB-21-0013991)
139 |  | SEAWEEDS PRODUCTION AND MARKETING |  | 12789862.17 | 2019-01-01 |  | 2021-12-31 |  | 100 | 12789862.17 | 0
(PRDP I-REAP)
140 |  | PUERTO PRINCESA CITY MANGO |  | 5441484.21 | 2018-01-01 |  | 2021-12-31 |  | 100 | 5441484.21 | 0
PROCESSING FACILITY AND MARKETING
CENTER - CIVIL WORKS (PRDP I-REAP)
141 |  | PUERTO PRINCESA CITY MANGO |  | 6711370.71 | 2018-01-01 |  | 2021-12-31 |  | 100 | 6711370.71 | 0
PROCESSING FACILITY AND MARKETING
CENTER - ENTERPRISE (PRDP I-REAP)
142 |  | CONSTRUCTION AND CONCRETING OF |  | 119829587.71 | 2020-01-01 |  | 2021-12-31 |  | 100 | 119829587.71 | 0
MARUYUGON TO BUENAVISTA FARM TO
MARKET ROAD (PRDP I-BUILD)
143 |  | DMCI POWER CORPORATION RWMHEEF (ER 1- |  | 1616861.19 | 2020-12-14 |  | 2022-12-31 |  | 94.8 | 1532839.7 | 0
94) - DMCI POWER IRAWAN
144 |  | DMCI POWER CORPORATION DLF (ER 1-94) - |  | 450734.62 | 2020-12-14 |  | 2022-12-31 |  | 77.67 | 350100 | 0
DMCI POWER IRAWAN
145 |  | DELTA P INCORPORATED DLF (ER 1-94) |  | 995103.08 | 2020-06-03 |  | 2022-12-31 |  | 27.14 | 270100.14 | 0
146 |  | DELTA P INCORPORATED RWMHEEF (ER 1-94) |  | 1548767.65 | 2020-06-03 |  | 2022-12-31 |  | 53.66 | 831096.86 | 0
147 |  | HC-CGPP PALAWAN POWER GEN INC. |  | 452705.3 | 2020-12-14 |  | 2022-12-31 |  | 0 | 0 | 0
RWMHEEF (ER 1-94)
148 |  | HC-CGPP PALAWAN POWER GEN INC. DLF |  | 452705.3 | 2020-12-14 |  | 2022-12-31 |  | 0 | 0 | 0
(ER-94)
149 |  | USAID - TUBERCULOSIS IMPLEMENTATION |  | 13354126.45 | 2022-06-13 |  | 2023-12-31 |  | 46.91 | 7089758.33 | 0 |  | 2434146
|  | FRAMEWORK AGREEMENT - TIFA | [10 empty] | 2315466.4
3792425.65
150 |  | SPECIAL RISK ALLOWANCE (SRA) - CY 2022 GAA |  | 3494318.18 | 2022-09-14 |  | 2022-12-31 |  | 77.97 | 2813190.05 | 0 |  | 817603.45
3994484.95
151 |  | CHIKITING BAKUNA DAYS (CBD) CULMINATION |  | 500000 | 2023-03-29 |  | 2023-06-30 |  | 0 | 0 | 0 |  | 13354126.45
ACTIVITY AND MID-YEAR PLANNING WORKSHOP
152 |  | LIVESTOCK REHABILITATION PROJECT |  | 26375000 | 2023-01-12 |  | 2023-12-31 |  | 0 | 0 | 0
153 |  | COMPLETION OF MANGINGISDA SATELLITE CLINIC |  | 3900000 | 2023-02-01 |  | 2023-12-31 |  | 0 | 0 | 0
PHASE 3, SAN MIGUEL SATELLITE CLINIC PHASE 3,
BAGONG BAYAN SATELLITE CLINIC PHASE 3, AND
NEW CONSTRUCTION OF PUERTO PRINCESA
SUPER HEALTH CENTER
154 |  | MAT (MEALS, ACCOMMODATION AND |  | 3900000 | 2022-05-12 |  | 2023-12-31 |  | 99.55 | 3882500 | 0
TRANSPORTATION) - HCWS
155 |  | LOTTO FUND UTILIZATION REPORT |  | 1824810.43 | 2021-11-02 |  | 2023-12-31 |  | 0 | 0 | 0
156 |  | STL FUND UTILIZATION REPORT |  | 958191.04 | 2021-07-12 |  | 2023-12-31 |  | 0 | 0 | 0
| TOTAL |  |  | 1218315864.35 | [5 empty] | 1157607387.18
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CHARLITO B. PADUL |  |  |  |  | LUCILO R. BAYRON
City Accountant |  |  |  |  | Local Chief Executive