## 2019 20% IRA U. 4th Qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
for the 4th Quarter, CY 2019
City of Puerto Princesa
Program/ Project |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incured to Date
ECONOMIC SERVICES
8918-83-1 | PURCHASE OF HEAVY EQPT. (SB#1)
2.0 Capital Outlay
| Construction and Heavy Equipment |  | 8466370.91 | [5 empty] | Bidded
8918-83-3 | PURCHASE OF 1 BRAND NEW MOBILE CONCRETE BATCHING PLANT (SB#2)
2.0 Capital Outlay
| Construction and Heavy Equipment |  | 13620000 | [5 empty] | Bidded
8918-83-4 | PURCHASE OF 1 UNIT BRAND NEW MOBILE CRUSHER FOR ROAD
CONCRETING PROJECTS (60 TONS/HR.) (SB#2)
2.0 Capital Outlay
| Construction and Heavy Equipment |  | 26600000 | [5 empty] | Bidded
8918-83-6 | PURCHASE OF 1 UNIT FIELD DENSITY TEST EQPT. & OTHER APPARATUS FOR
MATERIALS TESTING & QUALITY CONTROL (COMPLETE SET) (SB#2)
2.0 Capital Outlay
| Construction and Heavy Equipment |  | 7520000 |  |  |  | 7512788 |  | Purchased
8918-38 | CONSTRUCTION OF STREET LIGHTING FACILITIES (SB#2)
2.0 Capital Outlay
| Construction and Heavy Equipment |  | 86000000 | [5 empty] | Bidded
8918-83-5 | PURCHASE OF 1 UNIT BRAND NEW WATER TRUCK FOR ROAD CONCRETING
PROJECTS (SB#2)
2.0 Capital Outlay
| Construction and Heavy Equipment |  | 3800000 | [5 empty] | Bidded
8918-184 | ROAD WIDENING & CONCRETING OF ROAD NETWORKS PHASE I,
(FROM NAT'L. HIGHWAY TO SEASHORE) BGY. INAGAWAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Inagawan | 65850000 | 2019-03-29 | 365 CD | 78.61% | 41859588.79 |  | On-going (By contract)
8918-185 | CONCRETING OF DIAZ ROAD, BGY. MILAGROSA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Milagrosa | 6549000 | 2019-02-06 | 75 CD | 60% | 4267309.11 |  | On-going (By contract)
8918-169-1 | COMPLETION OF PSU TO RAFOLS ROAD PHASE III, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 60000000 | [5 empty] | Changed to by admin
8918-186 | CONCRETING OF 4-LANE ACCESS ROAD FROM PUERTO PRINCESA SOUTH
ROAD TO CITY HALL, ROTONDA, BALAYONG PARK, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 35000000 | 2019-10-13 | 270 CD | 5.52% | 5216748.62 |  | Bidded
8918-187 | CONCRETING OF ACCESS ROAD BETWEEN PSU AND SPORTS COMPLEX
BGY. TINIGUIBAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Tiniguiban | 9208301.87 | [5 empty] | POW for revision
8918-188 | CONCRETING OF MANTURON ROAD (FROM HIGHWAY TO SATELLITE CLINIC),
BGY. CABAYUGAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Cabayugan | 4569000 | 2019-02-18 | 45 CD | 100% | 4506545.51 |  | Completed
8918-189 | CONCRETING OF ACCESS ROAD TO NEW CITY CEMETERY, BGY. STA. LOURDES
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Lourdes | 11460000 | 2019-03-18 | 90 CD | 100% | 11297509.96 |  | Completed
8918-190 | OLANGUAN ROAD DEVELOPMENT PHASE II, BGY. BINDUYAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Binduyan | 2625000 | 2019-02-18 | 60 CD | 100% | 2617233.77 |  | Completed
8918-191 | CONCRETING OF CAIMITO ROAD WEST, BGY. SAN JOSE
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Jose | 13569000 | 2019-02-06 | 75 CD | 100% | 13522642.36 |  | Completed
8918-192 | CONCRETING OF KATIPUSDAN-MITRA ROAD, BGY. TAGBUROS
| 2.0 Capital Outlay | Bgy. Tagburos
| Public Infra - Road Networks | & Bgy. Sta Monica | 19340000 | 2019-02-04 | 90 CD | 90.06% | 17611087.91 |  | On-going (By contract)
8918-15-1 | CONCRETING OF PABLICO ROAD III, BGY. TINIGUIBAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Tiniguiban | 5459170.25 | 2019-02-06 | 60 CD | 100% | 5180888.41 |  | Completed
8918-193 | PROPOSE RE-ALIGNMENT OF CONCRETE ROAD WITH SLOPE PROTECTION
AND EMBANKMENT, GOLDEN VALLEY, BGY. SICSICAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sicsican | 1882776.64 | 2019-02-06 | 50 CD | 100% | 1841384.89 |  | Completed
8918-88-1 | CONCRETING OF MACOPA ROAD, EMPLOYEES VILLAGE, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 1819600 | 2019-02-18 | 45 CD | 80.06% | 259407.82 |  | On-going (By contract)
8918-96-1 | CONCRETING OF APITONG ROAD PHASE II, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 3236000 | 2019-03-15 | 45 CD | 80.31% | 2554773.65 |  | On-going (By contract)
8918-92-1 | CONCRETING OF EMPLOYEES VILLAGE PHASE II, BGY. SAN JOSE
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Jose | 12620000 | 2019-03-18 | 120 CD | 87.47% | 12511470.74 |  | On-going (By contract)
8918-194 | CONCRETING OF ROADS LEADING TO GOVERNMENT CENTERS, BGY. NAPSAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Napsan | 2901700 | [5 empty] | Bidded
8918-195 | CONCRETING OF ROADS LEADING TO GOVERNMENT CENTERS,
BGY. LUZVIMINDA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Luzviminda | 4139400 |  | 45 CD |  | 1043827.12 |  | Materials for delivery
8918-196 | CONCRETING OF MATIYAGA ROAD (SALVE REGINA), PUROK KAAKBAYAN, | [7 empty] | (By admin)
BGY. TINIGUIBAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Tiniguiban | 6041500 | 2019-03-18 | 60 CD | 95.79% | 5562355.39 |  | On-going (By contract)
8918-197 | CONCRETING OF TAYLOR ROAD, BGY. SAN PEDRO
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Pedro | 4544000 | 2019-02-06 | 45 CD | 100% | 3691996.12 |  | Completed
8918-198 | CONCRETING OF PALAY (PEO ROAD) BGY. BANCAO-BANCAO
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Bancao-Bancao | 5991000 | 2019-03-19 | 60 CD | 100% | 5492426.07 |  | Completed
8918-199 | CONCRETING OF TUMBAGA ROAD, BGY. SAN JOSE
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Jose | 7760000 | 2019-02-06 | 75 CD | 100% | 7702893.49 |  | Completed
8918-200 | OPENING OF TAGKURIRING ROAD, BGY. SIMPOCAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Simpocan | 4701854.17 | [5 empty] | No bidder. Changed to
8918-201 | CONSTRUCTION AND INSTALLATION OF ROAD TRAFFIC SIGNAGES | [7 empty] | by admin
(FOR BUKANG LIWAYWAY-MAKANDRING FMR)
2.0 Capital Outlay
| Other Road Network Facilities | Bgy. Langogan | 296109 |  |  |  | 226680.38 |  | Materials for delivery
8918-202 | CONCRETING OF ROAD TO WHARF & BGY. HALL, BGY. BAGONG BAYAN | [7 empty] | (By admin)
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Bagong Bayan | 1125000 | [5 empty] | Scheduled for bidding
8918-108-1 | CONCRETING OF SAN CARLOS ROAD PHASE II, BGY. BACUNGAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Bacungan | 7500000 | 2019-03-14 | 90 CD | 100% | 5021142.7 |  | Completed
8918-203 | CONCRETING OF LUZVIMINDA ROAD TO PUROK KAPALARAN,
BGY. LUZVIMINDA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Luzviminda | 15000000 | 2019-02-18 | 90 CD | 100% | 14073847.23 |  | Completed
8918-204 | CONCRETING OF MANGINGISDA ROAD (IGLESIA TO BGY. HALL)
BGY. MANGINGISDA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Mangingisda | 23883300 | 2019-06-14 | 150CD | 100% | 23583197.79 |  | Completed
8918-205 | CONCRETING OF VILLA TERESA FEEDER ROAD, SITIO MELWANG,
BGY. LUCBUAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Lucbuan | 21672000 | 2019-02-18 | 90 CD | 100% | 21073286.61 |  | Completed
8918-206 | CONCRETING OF MANALO TO SEASHORE ROAD, BGY. MANALO
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Manalo | 15000000 | 2019-02-18 | 75 CD | 100% | 14981400.11 |  | Completed
8918-207 | CONCRETING OF ROAD TO AGRI-TRADING CENTER, BGY. IRAWAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Irawan | 31885287.14 | 2019-03-20 | 210 CD | 100% | 29676407.72 |  | Completed
8918-208 | CONCRETING OF GUMAMELA ROAD, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 6549500 | 2019-03-06 | 60 CD | 100% | 6507500.4 |  | Completed
8918-209 | CONCRETING OF ROAD FROM HIGHWAY TO COVERED COURT,
BGY. CONCEPCION
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Concepcion | 858000 | 2019-10-07 | 30 CD | 100% |  |  | Completed
8918-210 | CONCRETING OF BAY VISTA ROAD, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 11499853.34 | 2019-02-04 | 75 CD | 98.37% | 6845512.96 |  | On-going. Subject for
8918-211 | CONCRETING OF BAHINTING ROAD, BGY. SAN MANUEL | [7 empty] | variation (By contract)
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Manuel | 10970000 | 2019-03-20 | 90 CD | 100% | 10575032.12 |  | Completed
8918-212 | CONCRETING OF MACAWILI ROAD, BGY. BANCAO-BANCAO
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Bancao-Bancao | 6844000 | 2019-02-11 | 75 CD | 67.98% | 4973499.09 |  | Suspended due to
8918-213 | CONCRETING OF PERIMETER ROAD, BGY. INAGAWAN-SUB | [7 empty] | embankment (By contract)
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Inagawan-Sub | 19263000 | 2019-03-05 | 90 CD | 100% | 14400421.18 |  | Completed
8918-214 | CONCRETING OF MAOYON ROAD, BGY. MAOYON
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Maoyon | 7367000 | 2019-06-03 | 60CD | 100% | 1005149.46 |  | Completed
8918-215 | CONCRETING OF ROAD FROM HIGHWAY TO PSU, BGY. SAN RAFAEL
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Rafael | 7759500 | 2019-02-04 | 75 CD | 8.68% | 1159071.38 |  | On-going (By contract)
8918-216 | CONCRETING OF MARUGADING TO BAYBAY ROAD, BGY. MARUYOGON
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Maruyogon | 10524000 | 2019-03-21 | 75 CD | 60.43% | 6521350.66 |  | On-going (By contract)
8918-217 | CONCRETING OF NATIVE ROAD TO VILLAGE, BGY. SALVACION
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Salvacion | 10929000 | 2019-02-05 | 60 CD | 100% | 1492338.24 |  | Completed
8918-218 | REHABILITATION OF ROAD (SUGOD I AND II) BGY. CABAYUGAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Cabayugan | 1220000 | [5 empty] | No bidder. Changed to
8918-219 | CONCRETING OF ROAD FROM HIGHWAY TO BGY. HALL TO COVERED COURT, | [7 empty] | by admin
BGY. TANABAG
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Tanabag | 4869200 | 2019-03-06 | 60 CD | 100% | 4815732.83 |  | Completed
8918-220 | CONCRETING OF BAHILE TO HIGH SCHOOL ROAD, BGY. BAHILE
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Bahile | 6537000 | 2019-03-15 | 60 CD | 100% | 6484561.39 |  | Completed
8918-183 | CONCRETING OF LANGONGAN GYM ROAD WITH PARKING AND
DRAINAGE SYSTEM, BGY. LANGOGAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Langogan | 4812756.59 |  | 60 CD |  | 3930112.84 |  | Materials for delivery
8918-13-2 | CONCRETING OF APAN ROAD PHASE II (Leading to Bgy. Mabuhay Relocation Site), | [7 empty] | (By admin)
BGY. SICSICAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sicsican | 9966000 | 2019-02-06 | 60 CD | 100% | 9776660.67 |  | Completed
8918-221 | CONSTRUCTION OF NEW MARKET STP (SB#2)
2.0 Capital Outlay
| Markets |  | 10000000 | [5 empty] | POW for revision
|  | GRAND TOTAL | 681604179.91 |  |  |  | 341375783.49
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
APPROVED:
ENGR. ALBERTO P. JIMENEZ | REGINA S. CANTILLO
City Engineer/Vice Chairman | City Budget Officer | LUCILO R. BAYRON
City Mayor