## Edit (hidden)
By Contract | Awarded
By Contract | Awarded

## Sheet1 (hidden)
By Contract | Awarded
By Contract | Awarded

## 4th Quarter 2023
Annex D
LOCAL GOVERNMENT SUPPORT FUND
Report on Fund Utilization and Status of Program/Project Implementation
As of December 31, 2023
Fund Source | Date of Notice of Authority to Debit Account Issued (NADAI) | Type of Program/Project | Name of Title of Program/Poject | Specific Location | Mechanism/ Mode of Implementation | Estimated Number of Beneficiaries | Amount |  |  | Estimated Period of Completion (month and year) | Program/Project Status
[7 empty] | Received | Obligation | Disbursement
NADAI for LGSF - AC BATCH 7 | 2019-03-04 | LGSF-AC/Green Green Green Program | Development of Balayong Nature Park | Green City Hall Complex, Bgy. Sta. Monica, Puerto Princesa | By Contract |  | 86865534 | 86834451.4 | 86865534 | December 2020 | 100%
NADAI for LGSF - AC BATCH 12 | 2020-08-17 | Local Government Support Fund - Assistance to Cities (LGSF-AC) | Development of Balayong Nature Park "Recreational Park with Green Parking Space" | Bgy. Sta. Monica, Puerto Princesa City, Palawan | By Contract |  | 20857070 | 19995201.25 | 17995681.13 | June 2022 | 86.28%
NADAI for LGSF - AC BATCH 13 | 2020-08-17 | Local Government Support Fund - Assistance to Cities (LGSF-AC) | Development of Mini Parks (Cascading Park, Friendship Park, PSU Gateway Park and Rotunda Park) | Bgy. Sta. Monica, Puerto Princesa City, Palawan | By Contract |  | 16762351 | 16749204.48 | 16762351 | December 2021 | 100%
SARO-OSEC-21-0001037 | September 21, 2021 | Local Government Support Fund (LGSF) - Other Financial Assistance to LGUs | Installation of Solar Street Lights in Rural Areas of Puerto Princesa City | Various Barangays, Puerto Princesa City, Palawan | By Administration |  | 10000000 | 9989072.8 | 10000000 | February 2022 | 100%
SARO-LGRCB-22-0003988 | 2022-05-27 | Local Government Support Fund (LGSF) - Financial Assistance to LGUs | Installation of Solar Street Lights in Barangay Bacungan and Barangay Sta. Lourdes | Bgy. Bacungan and Bgy. Sta. Lourdes, Puerto Princesa City, Palawan | By Administration |  | 20000000 | 19994810.16 | 20000000 | January 2023 | 100%
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Concreting of Farm-to-Market Road at Bgy. Marufinas | Bgy. Marufinas, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 6226442.03 | 5214645.21 | November 2023 | 78.93%
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Solar Electrification at Bgy. New Panggangan | Bgy. New Panggangan, Puerto Princesa City, Palawan |  |  | 6606882.16 | 0 | 0 |  | 0%
SARO-LGRCB-23-0017442 | 2023-06-06 | Local Government Support Fund - Support to the Barangay Development Program of NTF-ELCAC | Rehabilitation of Farm-to-Market Road at Bgy. Tagabinit | Bgy. Tagabinit, Puerto Princesa City, Palawan | By Contract |  | 6606882.16 | 1817052.62 | 1521781.58 | October 2023 | 23.03%
Certified correct by: | [6 empty] | Attested by:
MARIA REGINA S. CANTILLO |  |  |  | RAMIL V. GONZALES |  |  |  | LUCILO R. BAYRON
City Budget Officer |  |  |  | Acting Assistant City Accountant |  |  |  | City Mayor
JEROME M. PADRONES
City Treasurer
JOVENEE C. SAGUN
City Planning and Development Coordinator
Note on D12: Rodolfo H. Sayang: CIP Acct: 10710020-01-2021-09-652