## Form 7 - DFU
FDP Form 7 - 20% COMPONENT OF THE IRA UTILIZATION
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
| REGION: |  | MIMAROPA |  |  | CALENDAR YEAR: | 2026
| PROVINCE: |  | PALAWAN |  |  | QUARTER: | 2
| CITY/MUNICIPALITY: |  | CITY OF PUERTO PRINCESA
Code | Program / Project |  |  |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extension, if any | Remarks
[9 empty] | % of | Total Cost
[9 empty] | Completion | Incurred to Date
ECONOMIC DEVELOPMENT
8918-1(26) | CONSTRUCTION OF OPEN PARKING WITH PERIMETER FENCE AT ESH COLISEUM, BGY. SAN PEDRO
2.0 Capital Outlay
|  | Other Land Improvements |  |  | San Pedro | 5000000 | [5 empty] | For bidding
8918-2(26) | SITE DEVELOPMENT OF SAN JOSE PUBLIC MARKET (ROAD, PARKING, SIDEWALK, DRAINAGE AND STREETLIGHT), BGY. SAN JOSE
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Other Land Improvements |  |  | San Jose | 37057000 | 2026-05-26 | 2027-10-02 | 1.51% |  |  | By contract
8918-3(26) | IMPROVEMENT OF CITY MOTORPOOL COMPOUND (ROAD, PARKING, FENCE, GATE AND SLOPE PROTECTION), BGY. STA. MONICA
2.0 Capital Outlay
|  | Other Land Improvements |  |  | Sta. Monica | 48550500 | [5 empty] | Unimplemented
8918-4(26) | CONSTRUCTION OF PUERTO PRINCESA CITY MEMORIAL GARDEN PHASE VII, BGY. STA. LOURDES
2.0 Capital Outlay
|  | Other Land Improvements |  |  | Sta. Lourdes | 30000000 | [5 empty] | For bidding
8918-5(26) | CONSTRUCTION OF PERIMETER FENCE AND COLUMBARIUM AT OLD CITY CEMETERY, BGYS. MASIPAG AND MAUNLAD
|  | 2.0 Capital Outlay |  |  | Masipag & Maunlad
|  | Other Land Improvements |  |  |  | 50000000 | [5 empty] | Unimplemented
8918-6(26) | RECONSTRUCTION AND WIDENING OF KAMUNING-INAGAWAN ROAD WITH SIDEWALK AND DRAINAGE SYSTEM, BGYS. KAMUNING AND INAGAWAN
|  | 2.0 Capital Outlay |  |  | Kamuning & Inagawan
|  | Road Networks |  |  |  | 111878760 | [5 empty] | Unimplemented
8918-7(26) | ROAD REBLOCKING OF SAN PEDRO-SAN MANUEL PARALLEL ROAD (MACOPA STREET TO SANTOL ROAD), BGY. SAN JOSE
2.0 Capital Outlay
|  | Road Networks |  |  | San Jose | 21413375 | [5 empty] | Unimplemented
8918-8(26) | CONCRETING OF CROSS ROAD 2 FROM PUROK KAPALARAN TO PUROK KAUNLARAN, BGY. LUZVIMINDA
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Road Networks |  |  | Luzviminda | 24222920 | 2026-05-11 | 2027-02-18 | 10.83% | 1290 |  | By contract
8918-9(26) | CONCRETING OF ROAD SHOULDER AT TAFT STREET (CATHEDRAL-SANDOVAL-CONCEPCION), VARIOUS BARANGAYS
2.0 Capital Outlay
|  | Road Networks |  |  | Luzviminda | 2500000 | [5 empty] | Unimplemented
8918-10(26) | ROAD REBLOCKING OF RENGEL ROAD (RIZAL AVENUE TO MANALO STREET), BGY. BANCAO-BANCAO
|  | 2.0 Capital Outlay |  |  | Various
|  | Road Networks |  |  | Barangays | 9831642 | [5 empty] | Unimplemented
8918-11(26) | CONCRETING OF ROAD I, II AND III AT GOLDEN VALLEY RELOCATION SITE (QUITO - PHASE IV), BGY. SICSICAN
2.0 Capital Outlay
|  | Road Networks |  |  | Sicsican | 7202739 | [5 empty] | Unimplemented
8918-12(26) | CONCRETING OF YELLOWBELL STREET, BGY. SAN MIGUEL
2.0 Capital Outlay
|  | Road Networks |  |  | San Miguel | 1389000 | [5 empty] | Unimplemented
8918-13(26) | CONCRETING OF FISHERMAN'S VILLAGE ROAD NETWORKS, BGY. STA. MONICA
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Road Networks |  |  | Sta. Monica | 7641000 | 2026-04-22 | 2026-07-19 | 48.8% | 1290 |  | By contract
8918-14(26) | CONCRETING OF PERIMETER ROAD AT PUROK BAYBAY WITH BREAKWATER AND DRAINAGE SYSTEM, BGY. BABUYAN
2.0 Capital Outlay
|  | Road Networks |  |  | Babuyan | 5152700 | [5 empty] | Unimplemented
8918-15(26) | ASPHALT OVERLAY OF BONOAN ROAD, BGY. TAGUMPAY
2.0 Capital Outlay
|  | Road Networks |  |  | Tagumpay | 2316500 | [5 empty] | Unimplemented
8918-16(26) | ASPHALT OVERLAY OF QUEZON STREET, BGY. MALIGAYA
2.0 Capital Outlay
|  | Road Networks |  |  | Maligaya | 7197500 | [5 empty] | Unimplemented
8918-17(26) | ROAD REBLOCKING OF MACOPA ROAD (MUSLIM CEMETERY TO BAPTIST CHURCH), BGY. SAN JOSE
2.0 Capital Outlay
|  | Road Networks |  |  | San Jose | 4017043 | [5 empty] | Unimplemented
8918-18(26) | ROAD REBLOCKING OF MABINI STREET (OLIVEROS TO VALENCIA STREET), BGYS. MAUNLAD AND BAGONG SIKAT
2.0 Capital Outlay
|  | Road Networks |  |  | Bagong Sikat | 7220209 | [5 empty] | Unimplemented
8918-19(26) | CONCRETING OF MAIN CIRCULATION ROAD OF STA. LOURDES RESETTLEMENT PROJECT (ZOST SUBDIVISION), BGY. STA. LOURDES
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Road Networks |  |  | Sta. Lourdes | 17018200 | 2026-04-21 | 2026-11-16 | 37.72% |  |  | By contract
8918-20(26) | OPENING AND GRAVELLING OF PUROK TRES FMR, BGY. INAGAWAN SUB-COLONY
2.0 Capital Outlay
|  | Road Networks |  |  | Inagawan Sub | 4312500 | [5 empty] | Unimplemented
8918-21(26) | CONCRETING OF ACCESS ROAD FROM PUROK TAWIRAN TO CALTEX DEPOT, BGY. LUZVIMINDA
2.0 Capital Outlay
|  | Road Networks |  |  | Luzviminda | 74662500 | [5 empty] | Unimplemented
8918-22(26) | CONCRETING OF TAGBARUNGIS ROAD (ELEMENTARY SCHOOL TO RIVERSIDE), BGY. INAGAWAN SUB-COLONY
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Road Networks |  |  | Inagawan Sub | 21541750 | 2026-05-11 | 2027-01-02 | 4.57% |  |  | By contract
8918-23(26) | UPGRADING/MODIFICATION OF TAGNAYA HANGING BRIDGE 2, BGY. CONCEPCION
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Road Networks |  |  | Conception | 12000000 | 2026-04-22 | 2026-11-17 | 8.03% | 1290 |  | By contract
8918-24(26) | CONSTRUCTION OF SIDEWALK WITH DRAINAGE SYSTEM ALONG VALENCIA STREET (MANALO TO BONIFACIO), BGY. MASIPAG
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Road Networks |  |  | Masipag | 7332240 | 2026-04-30 | 2026-11-25 | 30.18% |  |  | By contract
8918-25(26) | CONSTRUCTION OF DRAINAGE SYSTEM AT SITIO SABANG, BGY. CABAYUGAN
2.0 Capital Outlay
|  | Road Networks |  |  | Cabayugan | 11013000 |  |  |  | 1030 |  | Unimplemented
8918-26(26) | CONSTRUCTION OF SLOPE PROTECTION FOR MAOYON ACCESS ROAD, BGY. MAOYON
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Road Networks |  |  | Maoyon | 14225500 | 2026-05-05 | 2027-11-30 | 27.14% | 1030 |  | By contract
8918-27(26) | COMPLETION OF SAN JOSE MARKET BY-PASS ROAD (SIDEWALK, PAVED SHOULDER AND DRAINAGE SYSTEM), BGY. SAN JOSE
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Road Networks |  |  | San Jose | 37688500 | 2026-03-23 | 2027-03-17 | 26.12% |  |  | By contract
8918-28(26) | RECONSTRUCTION/UPGRADING OF MACARASCAS-SABANG ROAD (ROAD REBLOCKING AND SLOPE PROTECTION) PHASE II, VARIOUS BARANGAYS
|  | 2.0 Capital Outlay |  |  | Various
|  | Road Networks |  |  | Barangays | 56920993 | [5 empty] | Unimplemented
8918-29(26) | CONSTRUCTION OF SIDEWALK WITH DRAINAGE SYSTEM ALONG SAMPALOC ROAD, BGY. SAN JOSE
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Road Networks |  |  | San Jose | 38312500 | 2026-03-23 | 2026-11-02 | 45.65% | 5686881.36 |  | By contract
8918-30(26) | CONSTRUCTION OF SLOPE PROTECTION FOR TAGNAYA HANGING BRIDGE 1, BGY. CONCEPCION
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Road Networks |  |  | Conception | 11000000 | 2026-05-05 | 2026-10-31 | 97.74% | 1030 |  | By contract
8918-31(26) | CONSTRUCTION OF CONCRETE FOOTBRIDGE FROM PUROK PAG-ASA TO PUROK PAGKAKAISA, BGY. MARUFINAS
2.0 Capital Outlay
|  | Road Networks |  |  | Marufinas | 6350000 |  |  |  | 1290 |  | For bidding
8918-32(26) | CONCRETING OF ROAD FROM MT. CALVARY ACCESS ROAD, BGY. IRAWAN
2.0 Capital Outlay
|  | Road Networks |  |  | Irawan | 6500000 | [5 empty] | Unimplemented
8918-33(26) | CONSTRUCTION AND REHABILITATION OF WATER SUPPLY SYSTEM AT SITIO STO. NIÑO, BGY. NAPSAN
2.0 Capital Outlay
|  | Water Supply System |  |  | Napsan | 5310000 | [5 empty] | Unimplemented
8918-34(26) | CONSTRUCTION AND REHABILITATION OF WATER SUPPLY SYSTEM AT SITIO TAGKURIRING, BGY. SIMPOCAN
2.0 Capital Outlay
|  | Water Supply System |  |  | Simpocan | 6500000 | [5 empty] | Unimplemented
8918-35(26) | SUPPLY AND INSTALLATION OF INTEGRATED SOLAR STREETLIGHTS WITH LAMP POST, VARIOUS BARANGAYS
|  | 2.0 Capital Outlay |  |  | Various
|  | Other Infrastructure Assets |  |  | Barangays | 45000000 |  |  |  | 1290 |  | Unimplemented
8918-36(26) | SUPPLY AND INSTALLATION OF UP LIGHT FOR BALAYONG TREES, BGY. STA. MONICA
2.0 Capital Outlay
|  | Other Infrastructure Assets |  |  | Sta. Monica | 2500000 | [5 empty] | Unimplemented
8918-37(26) | SUPPLY AND INSTALLATION OF LED LIGHTINGS AT ACACIA TUNNEL, BGY. INAGAWAN
2.0 Capital Outlay
|  | Other Infrastructure Assets |  |  | Inagawan | 3000000 | [5 empty] | Unimplemented
8918-38(26) | SUPPLY AND INSTALLATION OF INTEGRATED SOLAR STREETLIGHTS WITH LAMP POST AT BALAYONG PARK, BGY. STA. MONICA
2.0 Capital Outlay
|  | Other Infrastructure Assets |  |  | Sta. Monica | 19500000 | [5 empty] | Unimplemented
8918-39(26) | SUPPLY AND INSTALLATION OF INTEGRATED SOLAR STREETLIGHTS WITH LAMP POST AT TAGKAWAYAN CITY BEACH, BGY. BACUNGAN
2.0 Capital Outlay
|  | Other Infrastructure Assets |  |  | Bacungan | 5550000 | [5 empty] | Unimplemented
8918-40(26) | CONSTRUCTION OF DRAINAGE SYSTEM AT TAGBARUNGIS ELEMENTARY AND HIGH SCHOOL, BGY. INAGAWAN SUB-COLONY
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Other Infrastructure Assets |  |  | Inagawan Sub | 23902770 | 2026-05-05 | 2026-12-30 | 8.04% | 1030 |  | By contract
8918-41(26) | CONSTRUCTION OF SLOPE PROTECTION AT CITY EMPLOYEES VILLAGE COVERED COURT, BGY. STA. MONICA
2.0 Capital Outlay
|  | Other Infrastructure Assets |  |  | Sta. Monica | 593000 | [5 empty] | Unimplemented
8918-42(26) | CONSTRUCTION OF CITY ENGINEERING AND ARCHITECTURE BUILDING AUXILIARY (ELEVATOR, ELECTRONICS WORK AND COVERED FABRICATION SHED), BGY. STA. MONICA
2.0 Capital Outlay
|  | Buildings |  |  | Sta. Monica | 35000000 | [5 empty] | For bidding
8918-43(26) | CONSTRUCTION OF CITY SPORTS OFFICE (PUBLIC TOILET AND STORAGE), BGY. STA. MONICA
2.0 Capital Outlay
|  | Buildings |  |  | Sta. Monica | 30000000 | [5 empty] | For bidding
8918-44(26) | IMPROVEMENT AND REPAIR OF GREEN CITY HALL BUILDING (MAIN ROOF REPLACEMENT, MECHANICAL, WATER SYSTEM, POWER SUPPLY, FENCE, OUTPOST AND REPAINTING), BGY. STA. MONICA
2.0 Capital Outlay
|  | Buildings |  |  | Sta. Monica | 30000000 | [5 empty] | For bidding
8918-45(26) | CONVERSION OF OCTAGONAL TOILET TO CAFE AT INTERACTIVE WATER PARK, BGY. STA. MONICA
2.0 Capital Outlay
|  | Buildings |  |  | Sta. Monica | 5857280 | 2026-06-23 | 2026-12-19 |  |  |  | Project awarded
8918-46(26) | CONSTRUCTION OF STANDARD DAY CARE CENTER, BGY. BAHILE
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | School Buildings |  |  | Bahile | 6234113 | 2026-05-05 | 2026-10-01 | 30.79% |  |  | By contract
8918-47(26) | CONSTRUCTION OF STANDARD DAY CARE CENTER, BGY. SICSICAN | [10 empty] | Project suspended due to finalization of exact location
2.0 Capital Outlay
|  | School Buildings |  |  | Sicsican | 6406469 | 2026-05-05 | 2026-10-01
8918-48(26) | CONSTRUCTION OF STANDARD DAY CARE CENTER AT PUROK NEW PRINCESA, BGY. TINIGUIBAN
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | School Buildings |  |  | Tiniguiban | 6113082 | 2026-03-30 | 2026-07-26 | 33.31% |  |  | By contract
8918-49(26) | CONSTRUCTION OF STANDARD DAY CARE CENTER, BGY. IRAWAN
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | School Buildings |  |  | Irawan | 5901131 | 2026-04-27 | 2026-09-23 | 28.51% |  |  | By contract
8918-50(26) | CONSTRUCTION OF STANDARD DAY CARE CENTER, BGY. SALVACION
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | School Buildings |  |  | Salvacion | 6000000 | 2026-05-05 | 2026-10-01 | 30.48% |  |  | By contract
8918-51(26) | CONSTRUCTION OF STANDARD DAY CARE CENTER, BGY. MACARASCAS
2.0 Capital Outlay
|  | School Buildings |  |  | Macarascas | 5856477 | [5 empty] | For bidding
8918-52(26) | CONSTRUCTION OF STANDARD DAY CARE CENTER AT SITIO BAYATAO, BGY. TAGABINET
2.0 Capital Outlay
|  | School Buildings |  |  | Tagabinet | 6500000 | [5 empty] | For rebidding
8918-53(26) | CONSTRUCTION OF STANDARD DAY CARE CENTER AT PUROK STO. NIÑO, BGY. NAPSAN
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | School Buildings |  |  | Napsan | 5995230 | 2026-05-13 | 2026-10-21 | 8.62% |  |  | By contract
8918-54(26) | SATELLITE CLINIC (ANCILLARY STRUCTURES), BGY. NAPSAN
2.0 Capital Outlay
|  | Hospitals and Health Centers |  |  | Napsan | 9803000 | [5 empty] | Unimplemented
8918-55(26) | COMPLETION OF MANGINGISDA SATELLITE CLINIC (FENCE, SITE DEVELOPMENT AND ANCILLARY STRUCTURES), BGY. MANGINGISDA
2.0 Capital Outlay
|  | Hospitals and Health Centers |  |  | Mangingisda | 20627000 | [5 empty] | Unimplemented
8918-56(26) | COMPLETION OF PUBLIC MARKET AT IRAWAN AGRICULTURAL CENTER, BGY. IRAWAN
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Markets |  |  | Irawan | 33000000 | 2026-05-20 | 2026-12-15 | 2.29% | 4896225 |  | By contract
8918-57(26) | CONSTRUCTION AND IMPROVEMENT OF FACILITIES AT CITY SLAUGHTERHOUSE COMPOUND, BGY. TAGBUROS
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Slaughterhouses |  |  | Tagburos | 3000000 | 2026-05-05 | 2026-10-31 | 36.7% |  |  | By contract
8918-58(26) | CONSTRUCTION OF PUBLIC TOILET, BGY. INAGAWAN SUB-COLONY
2.0 Capital Outlay
|  | Other Structures |  |  | Inagawan Sub | 1000000 |  |  |  | 745812.36 |  | For bidding
8918-59(26) | CONSTRUCTION OF COVERED COURT, BGY. SAN ISIDRO
|  | 2.0 Capital Outlay | [9 empty] | Project on-going
|  | Other Structures |  |  | San Isidro | 10500000 | 2026-04-29 | 2026-10-25 | 7.61% |  |  | By contract
8918-60(26) | CONSTRUCTION OF BLEACHERS WITH METAL BARRIER AT SWIMMING POOL AREA, BGY. STA. MONICA
2.0 Capital Outlay
|  | Other Structures |  |  | Sta. Monica | 14000000 | [5 empty] | For bidding
8918-61(26) | SUPPLY AND INSTALLATION OF BAYWALK MUSICAL FOUNTAIN (COMPLETE FOUNTAIN EQUIPMENT, POWER SUPPLY AND CIVIL WORKS), BGY. SAN ISIDRO
2.0 Capital Outlay
|  | Other Structures |  |  | San Isidro | 50000000 | [5 empty] | Unimplemented
8918-62(26) | OTHER DEVELOPMENT PROJECTS
2.0 Capital Outlay
|  | Other Structures |  |  |  | 451105
We hereby certify that we have reviewed the contents and hereby attest to | We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
the veracity and correctness of the data of information contained in this
document.
APPROVED:
|  | ENGR. ARIES S. GRANDE |  | REGINA S. CANTILLO
|  | City Engineer |  | City Budget Officer
LUCILO R. BAYRON
City Mayor